## Capa
SÃO PAULO STATE GOVERNMENT
State Secretariat for Investment Partnerships
SPI PROCESS nº 021.00000891/2024-87
INTERNACIONAL COMPETITION Nº 01/2024
PPP LOTE ALTO TIETÊ
EXHIBIT VIII.A – PHYSICAL EXECUTIVE SCHEDULE AND INVESTMENT PLAN

## ANEXO VIII.A
Total Capex | BRL thousand | Total | Year 1 | Year 2 | Year3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26 | Year 27 | Year 28 | Year 29 | Year 30
|  | 13961957951.1089 | 710852976.5201 | 1236526396.0841 | 2396140744.2309 | 3019488000.5072 | 2604190144.6503 | 1944327095.124 | 1122983766.6949 | 248580597.5331 | 5243483.5514 | 0 | 0 | 0 | 0 | 0 | 18201150.2576 | 241016494.8574 | 119426013.091 | 52140100.6885 | 80530773.9687 | 42625309.8713 | 12626355.1362 | 31687068.6035 | 73936493.4081 | 1434986.3304 | 0 | 0 | 0 | 0 | 0 | 0
1 | Stations - Civil Construction, Overhead Network, Permanent Track and Systems | 3109683323.2267 | 44689527.1426 | 81038749.1068 | 203467628.4151 | 579458313.549 | 546570745.086 | 879980654.5084 | 299606421.3127 | 0 | 5243483.5514 | 0 | 0 | 0 | 0 | 0 | 18201150.2576 | 142643111.2109 | 119426013.091 | 52140100.6885 | 80530773.9687 | 42625309.8713 | 12626355.1362 | 0 | 0 | 1434986.3304 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Construction on Line 11 Stations | 1477735120.3935 | 23579977.6661 | 65751183.6957 | 144791084.2892 | 370003279.687 | 344197744.4559 | 211366600.761 | 63373762.1627 | 0 | 5243483.5514 | 0 | 0 | 0 | 0 | 0 | 0 | 122491398.1585 | 116792130.7263 | 5193048.4371 | 4951426.8027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Station Bom Retiro | 282446636.8899 | 0 | 0 | 0 | 22577774.3136 | 77351626.8361 | 132851722.7943 | 37701336.5017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.1.1 | Mobilization, earth movement, retaining structures, and foundations | 22577774.3136 | 0 | 0 | 0 | 22577774.3136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.1.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 94826652.117 | 0 | 0 | 0 | 0 | 0 | 94826652.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.1.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 33114068.9932 | 0 | 0 | 0 | 0 | 0 | 0 | 33114068.9932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.3 | Overhead Network | 43099921.9584 | 0 | 0 | 0 | 0 | 30169945.3708 | 12929976.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.4 | Permanent Track | 67402402.0933 | 0 | 0 | 0 | 0 | 47181681.4653 | 20220720.628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.5 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | Station Lajeado | 161468375.0014 | 0 | 0 | 0 | 14376244.1949 | 30940650.7345 | 78514877.9667 | 25672425.661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.2.1 | Mobilization, earth movement, retaining structures, and foundations | 14376244.1949 | 0 | 0 | 0 | 14376244.1949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.2.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 60380225.6187 | 0 | 0 | 0 | 0 | 0 | 60380225.6187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.2.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 21085158.1526 | 0 | 0 | 0 | 0 | 0 | 0 | 21085158.1526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.3 | Overhead Network | 17239968.7833 | 0 | 0 | 0 | 0 | 12067978.1483 | 5171990.635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.4 | Permanent Track | 26960960.8373 | 0 | 0 | 0 | 0 | 18872672.5861 | 8088288.2512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.5 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3 | Station Brás | 57948115.2563 | 4135751.4291 | 0 | 9715963.9238 | 17828992.0269 | 14303231.4322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.1 | Initial Work | 4135751.4291 | 4135751.4291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.2 | Civil Construction | 32386546.4127 | 0 | 0 | 9715963.9238 | 12954618.5651 | 9715963.9238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.4 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4 | Station Guaianases | 48259809.0963 | 616573.9248 | 0 | 0 | 15361340.5646 | 15074234.6113 | 0 | 0 | 0 | 5243483.5514 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4.1 | Initial Work | 616573.9248 | 616573.9248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4.2 | Civil Construction | 26217417.7571 | 0 | 0 | 0 | 10486967.1028 | 10486967.1028 | 0 | 0 | 0 | 5243483.5514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4.3 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5 | Station Braz Cubas | 70043261.9445 | 507162.7824 | 0 | 7216542.2622 | 35183850.9628 | 15171529.4929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.1 | Initial Work | 507162.7824 | 507162.7824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.2.1 | Mobilization, earth movement, retaining structures, and foundations | 7216542.2622 | 0 | 0 | 7216542.2622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.2.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 30309477.5011 | 0 | 0 | 0 | 30309477.5011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.2.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 10584261.9845 | 0 | 0 | 0 | 0 | 10584261.9845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.3 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6 | Station Jundiapeba | 132783359.2071 | 0 | 0 | 10073491.8258 | 47183039.1301 | 63562651.8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.2.1 | Mobilization, earth movement, retaining structures, and foundations | 10073491.8258 | 0 | 0 | 10073491.8258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.2.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 42308665.6683 | 0 | 0 | 0 | 42308665.6683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.2.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 14774454.6778 | 0 | 0 | 0 | 0 | 14774454.6778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.3 | Overhead Network | 17239968.7833 | 0 | 0 | 0 | 0 | 17239968.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.4 | Permanent Track | 26960960.8373 | 0 | 0 | 0 | 0 | 26960960.8373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.5 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7 | Station Mogi das Cruzes | 130590354.4974 | 0 | 0 | 13788685.2449 | 62786851.4905 | 42050641.3177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.2.1 | Mobilization, earth movement, retaining structures, and foundations | 13788685.2449 | 0 | 0 | 13788685.2449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.2.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 57912478.0287 | 0 | 0 | 0 | 57912478.0287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.2.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 20223405.0259 | 0 | 0 | 0 | 0 | 20223405.0259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.3 | Overhead Network | 17239968.7833 | 0 | 0 | 0 | 0 | 17239968.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.4 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8 | Station Estudantes | 153698079.2514 | 0 | 0 | 13873713.7768 | 63143971.3242 | 64716217.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.2.1 | Mobilization, earth movement, retaining structures, and foundations | 13873713.7768 | 0 | 0 | 13873713.7768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.2.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 58269597.8624 | 0 | 0 | 0 | 58269597.8624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.2.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 20348113.5392 | 0 | 0 | 0 | 0 | 20348113.5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.3 | Overhead Network | 15515971.905 | 0 | 0 | 0 | 0 | 15515971.905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.4 | Permanent Track | 24264864.7536 | 0 | 0 | 0 | 0 | 24264864.7536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.5 | Telecom and Systems | 21425817.4145 | 0 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9 | Station Palmeiras-Barra Funda | 25592151.2428 | 2244218.0259 | 5835431.363 | 5548325.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9.1 | Initial Work | 2244218.0259 | 2244218.0259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9.2 | Civil Construction | 1922115.8024 | 0 | 961057.9012 | 961057.9012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.10 | Station Luz | 27861812.7314 | 168942.361 | 8007899.9397 | 7720793.9864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.10.1 | Initial Work | 168942.361 | 168942.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.10.2 | Civil Construction | 6267052.9559 | 0 | 3133526.4779 | 3133526.4779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.10.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11 | Station Tatuapé | 29906972.3943 | 2224864.3556 | 8002518.7739 | 7715412.8205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11.1 | Initial Work | 2224864.3556 | 2224864.3556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11.2 | Civil Construction | 6256290.6242 | 0 | 3128145.3121 | 3128145.3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.12 | Station Corinthians-Itaquera | 24835225.7934 | 1032558.8936 | 6062798.2045 | 5775692.2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.12.1 | Initial Work | 1032558.8936 | 1032558.8936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.12.2 | Civil Construction | 2376849.4854 | 0 | 1188424.7427 | 1188424.7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.12.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.13 | Station Dom Bosco | 32363706.5973 | 3024409.5222 | 8831113.2921 | 8544007.3388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.13.1 | Initial Work | 3024409.5222 | 3024409.5222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.13.2 | Civil Construction | 7913479.6606 | 0 | 3956739.8303 | 3956739.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.13.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.14 | Station José Bonifácio | 26909185.7637 | 2585621.4445 | 6323246.9141 | 6036140.9608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.14.1 | Initial Work | 2585621.4445 | 2585621.4445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.14.2 | Civil Construction | 2897746.9047 | 0 | 1448873.4524 | 1448873.4524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.14.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.15 | Station Antônio Gianetti Neto | 39786959.6456 | 1685578.0797 | 0 | 13212155.5375 | 12925049.5841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.15.1 | Initial Work | 1685578.0797 | 1685578.0797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.15.2 | Civil Construction | 16675564.1514 | 0 | 0 | 8337782.0757 | 8337782.0757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.15.3 | Telecom and Systems | 21425817.4145 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.16 | Station Ferraz of Vasconcelos | 25337908.195 | 2541350.7335 | 5559743.4853 | 5272637.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.16.1 | Initial Work | 2541350.7335 | 2541350.7335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.16.2 | Civil Construction | 1370740.0471 | 0 | 685370.0235 | 685370.0235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.16.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.17 | Station Poá | 23644407.1742 | 732627.8499 | 5617354.4167 | 5330248.4634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.17.1 | Initial Work | 732627.8499 | 732627.8499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.17.2 | Civil Construction | 1485961.9099 | 0 | 742980.955 | 742980.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.17.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.18 | Station Calmon Viana | 41771453.4227 | 2033567.8195 | 0 | 14030407.5561 | 13743301.6028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.18.1 | Initial Work | 2033567.8195 | 2033567.8195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.18.2 | Civil Construction | 18312068.1887 | 0 | 0 | 9156034.0943 | 9156034.0943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.18.3 | Telecom and Systems | 21425817.4145 | 0 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.19 | Station Suzano | 24997228.6241 | 46750.4444 | 6636703.8444 | 6349597.8911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.19.1 | Initial Work | 46750.4444 | 46750.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.19.2 | Civil Construction | 3524660.7653 | 0 | 1762330.3826 | 1762330.3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.19.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20 | Station Penha | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.2.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.3 | Telecom and Systems | 21425817.4145 | 0 | 4874373.4618 | 4587267.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6124569.9079 | 5839606.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20. | Station Cezar of Souza | 96064300.2501 | 0 | 0 | 0 | 64892864.4924 | 21026960.5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193048.4371 | 4951426.8027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.1.1 | Mobilization, earth movement, retaining structures, and foundations | 11684589.0096 | 0 | 0 | 0 | 11684589.0096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.1.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 49075273.8405 | 0 | 0 | 0 | 49075273.8405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.1.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 17137397.2141 | 0 | 0 | 0 | 0 | 17137397.2141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.20.2 | Telecom and Systems | 18167040.1859 | 0 | 0 | 0 | 4133001.6423 | 3889563.3038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193048.4371 | 4951426.8027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Construction on Line 12 Stations | 513323732.2714 | 15162669.2725 | 15287565.4111 | 58676544.1258 | 159001163.5044 | 78587045.0355 | 26609268.3879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18201150.2576 | 17354288.9722 | 0 | 36402300.5152 | 62010303.3308 | 26031433.4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 | Station Itaquaquecetuba | 181732789.6312 | 0 | 0 | 15854245.4374 | 118031653.0301 | 30069171.5488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.2.1 | Mobilization, earth movement, retaining structures, and foundations | 15854245.4374 | 0 | 0 | 15854245.4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.2.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 66587830.8371 | 0 | 0 | 0 | 66587830.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.2.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 23252893.3082 | 0 | 0 | 0 | 0 | 23252893.3082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.3 | Overhead Network | 17239968.7833 | 0 | 0 | 0 | 17239968.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.4 | Permanent Track | 26960960.8373 | 0 | 0 | 0 | 26960960.8373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.5.1.1 | Telecom and Systems | 31836890.4278 | 0 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2 | Station USP Leste | 36319581.1287 | 1792686.884 | 0 | 0 | 7242892.5723 | 9506282.0575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.1 | Initial Work | 1792686.884 | 1792686.884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.2 | Civil Construction | 2690003.8169 | 0 | 0 | 0 | 0 | 2690003.8169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.3 | Telecom and Systems | 31836890.4278 | 0 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.3 | Station Comendador Ermelino | 34257472.2642 | 1054952.1556 | 0 | 0 | 7242892.5723 | 8181907.9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.3.1 | Initial Work | 1054952.1556 | 1054952.1556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.3.2 | Civil Construction | 1365629.6808 | 0 | 0 | 0 | 0 | 1365629.6808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.3.3 | Telecom and Systems | 31836890.4278 | 0 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.4 | Station São Miguel Paulista | 34954914.6797 | 833296.7016 | 0 | 0 | 7242892.5723 | 9101005.7909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.4.1 | Initial Work | 833296.7016 | 833296.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.4.2 | Civil Construction | 2284727.5503 | 0 | 0 | 0 | 0 | 2284727.5503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.4.3 | Telecom and Systems | 31836890.4278 | 0 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.5 | Station Jardim Helena - Vila Mara | 34291039.0775 | 981266.8646 | 0 | 0 | 0 | 7242892.5723 | 8289160.0257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.5.1 | Initial Work | 981266.8646 | 981266.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.5.2 | Civil Construction | 1472881.7851 | 0 | 0 | 0 | 0 | 0 | 1472881.7851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.5.3 | Telecom and Systems | 31836890.4278 | 0 | 0 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.6 | Station Itaim Paulista | 36244559.9134 | 1645723.3437 | 0 | 0 | 0 | 7242892.5723 | 9578224.3825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.6.1 | Initial Work | 1645723.3437 | 1645723.3437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.6.2 | Civil Construction | 2761946.1419 | 0 | 0 | 0 | 0 | 0 | 2761946.1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.6.3 | Telecom and Systems | 31836890.4278 | 0 | 0 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.7 | Station Jardim Romano | 35374346.9176 | 1611850.7507 | 0 | 0 | 0 | 7242892.5723 | 8741883.9797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.7.1 | Initial Work | 1611850.7507 | 1611850.7507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.7.2 | Civil Construction | 1925605.7391 | 0 | 0 | 0 | 0 | 0 | 1925605.7391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.7.3 | Telecom and Systems | 31836890.4278 | 0 | 0 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.8 | Station Aracaré | 88312138.2312 | 0 | 8471287.1705 | 42822298.6884 | 19240832.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.8.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.8.2 | Civil Construction | 56475247.8033 | 0 | 8471287.1705 | 35579406.1161 | 12424554.5167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.8.3 | Telecom and Systems | 31836890.4278 | 0 | 0 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9 | Station Manoel Feio | 31836890.4278 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9.1 | Initial Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9.2 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9.3 | Telecom and Systems | 31836890.4278 | 7242892.5723 | 6816278.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100575.1288 | 8677144.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Construction on Line 13 Stations | 1118624470.5618 | 5946880.204 | 0 | 0 | 50453870.3576 | 123785955.5946 | 642004785.3594 | 236232659.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797424.0802 | 2633882.3648 | 10544751.7362 | 13569043.8353 | 16593876.413 | 12626355.1362 | 0 | 0 | 1434986.3304 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1 | Station Engenheiro Goulart | 17246147.5323 | 2714213.8331 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 2235564.1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1.1 | Initial Work | 2714213.8331 | 2714213.8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1.2 | Civil Construction | 2235564.1158 | 0 | 0 | 0 | 0 | 0 | 0 | 2235564.1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1.3 | Telecom and Systems | 12296369.5834 | 0 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.2 | Station Guarulhos-CECAP | 17022036.4854 | 3019522.5065 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 1706144.3954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.2.1 | Initial Work | 3019522.5065 | 3019522.5065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.2.2 | Civil Construction | 1706144.3954 | 0 | 0 | 0 | 0 | 0 | 0 | 1706144.3954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.2.3 | Telecom and Systems | 12296369.5834 | 0 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.3 | Station Guarulhos Airport | 15289501.8924 | 213143.8644 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 2779988.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.3.1 | Initial Work | 213143.8644 | 213143.8644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.3.2 | Civil Construction | 2779988.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 2779988.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.3.3 | Telecom and Systems | 12296369.5834 | 0 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.4 | Station Jardim Eucaliptos | 189623158.823 | 0 | 0 | 0 | 0 | 26706220.7777 | 114800961.0525 | 41648762.9879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.4.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.4.1.1 | Mobilization, earth movement, retaining structures, and foundations | 26706220.7777 | 0 | 0 | 0 | 0 | 26706220.7777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.4.1.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 112166127.2665 | 0 | 0 | 0 | 0 | 0 | 112166127.2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.4.1.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 39169123.8074 | 0 | 0 | 0 | 0 | 0 | 0 | 39169123.8074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.4.2 | Telecom and Systems | 11581686.9714 | 0 | 0 | 0 | 0 | 0 | 2634833.786 | 2479639.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5 | Station São João | 160666877.0679 | 0 | 0 | 0 | 0 | 22362778.5145 | 96558503.5468 | 35278381.0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5.1.1 | Mobilization, earth movement, retaining structures, and foundations | 22362778.5145 | 0 | 0 | 0 | 0 | 22362778.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5.1.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 93923669.7608 | 0 | 0 | 0 | 0 | 0 | 93923669.7608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5.1.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 32798741.8212 | 0 | 0 | 0 | 0 | 0 | 0 | 32798741.8212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5.2 | Telecom and Systems | 11581686.9714 | 0 | 0 | 0 | 0 | 0 | 2634833.786 | 2479639.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.6 | Station Presidente Dutra | 212199792.061 | 0 | 0 | 0 | 0 | 30092715.7634 | 129024239.9924 | 46615622.3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.6.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.6.1.1 | Mobilization, earth movement, retaining structures, and foundations | 30092715.7634 | 0 | 0 | 0 | 0 | 30092715.7634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.6.1.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 126389406.2064 | 0 | 0 | 0 | 0 | 0 | 126389406.2064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.6.1.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 44135983.1197 | 0 | 0 | 0 | 0 | 0 | 0 | 44135983.1197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.6.2 | Telecom and Systems | 11581686.9714 | 0 | 0 | 0 | 0 | 0 | 2634833.786 | 2479639.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.7 | Station Bonsucesso | 220223057.2881 | 0 | 0 | 0 | 0 | 31296205.5475 | 134078897.0855 | 48380740.6503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.7.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.7.1.1 | Mobilization, earth movement, retaining structures, and foundations | 31296205.5475 | 0 | 0 | 0 | 0 | 31296205.5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.7.1.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 131444063.2995 | 0 | 0 | 0 | 0 | 0 | 131444063.2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.7.1.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 45901101.4697 | 0 | 0 | 0 | 0 | 0 | 0 | 45901101.4697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.7.2 | Telecom and Systems | 11581686.9714 | 0 | 0 | 0 | 0 | 0 | 2634833.786 | 2479639.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310625.2208 | 3156588.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.8 | Station Cangaíba | 274057529.8284 | 0 | 0 | 0 | 39264174.0367 | 2797424.0802 | 167542183.6822 | 57587455.2539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.8.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.8.1.1 | Mobilization, earth movement, retaining structures, and foundations | 39264174.0367 | 0 | 0 | 0 | 39264174.0367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.8.1.2 | Structures, enclosures, non-apparent installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 164909530.9543 | 0 | 0 | 0 | 0 | 0 | 164909530.9543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.8.1.3 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 57587455.2539 | 0 | 0 | 0 | 0 | 0 | 0 | 57587455.2539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.8.2 | Telecom and Systems | 12296369.5834 | 0 | 0 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514917.2454 | 3351375.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.9 | Station Gabriela Mistral | 12296369.5834 | 0 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797424.0802 | 2633882.3648 | 0 | 0 | 0 | 0 | 0 | 0 | 1434986.3304 | 0 | 0 | 0 | 0 | 0 | 0
1.3.9.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.9.2 | Telecom and Systems | 12296369.5834 | 0 | 0 | 0 | 2797424.0802 | 2632652.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797424.0802 | 2633882.3648 | 0 | 0 | 0 | 0 | 0 | 0 | 1434986.3304 | 0 | 0 | 0 | 0 | 0 | 0
2 | Systems | 4044322410.9298 | 85385974.9299 | 373356329.7936 | 749175828.1159 | 700717507.9887 | 835947514.6522 | 670919151.0451 | 458060246.0211 | 170759858.3834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Energy | 1247110649.1828 | 45482083.3739 | 157068410.1183 | 81827960.3231 | 259851576.4195 | 342072463.0946 | 217014404.0374 | 115139762.592 | 28653989.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Energy - Tracks | 775946441.7859 | 0 | 0 | 12723356.0362 | 247736096.3929 | 186355943.6922 | 185337293.8487 | 115139762.592 | 28653989.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.2 | Segment Luz - km 0+000 / Brás km 2+240 (extension of 2.240 m of double track) | 17026163.7139 | 0 | 0 | 0 | 11918314.5997 | 5107849.1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.2.1 | Auxiliary Vehicles and Equipment | 11918314.5997 | 0 | 0 | 0 | 11918314.5997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.2.2 | Completion of installation / commissioning | 4256540.9285 | 0 | 0 | 0 | 0 | 4256540.9285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.2.3 | Final acceptance | 851308.1857 | 0 | 0 | 0 | 0 | 851308.1857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.3 | Segment Engenheiro Gualberto - km 8+500 / Corinthians Itaquera - km 19+450 (extension 10.950 m of double track) | 83230577.0836 | 0 | 0 | 0 | 58261403.9585 | 24969173.1251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.3.1 | Auxiliary Vehicles and Equipment | 58261403.9585 | 0 | 0 | 0 | 58261403.9585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.3.2 | Completion of installation / commissioning | 20807644.2709 | 0 | 0 | 0 | 0 | 20807644.2709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.3.3 | Final acceptance | 4161528.8542 | 0 | 0 | 0 | 0 | 4161528.8542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.5 | Segment Guaianazes km 24+800 / Suzano km 36+940 (Extension of 12.140m in double track. Railway TR 68 of km 25+000 to km 33+800 - Extension of 8.800m) | 33444250.1523 | 0 | 0 | 0 | 0 | 16387682.5746 | 7023292.532 | 8361062.5381 | 1672212.5076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.5.1 | Auxiliary Vehicles and Equipment | 23410975.1066 | 0 | 0 | 0 | 0 | 16387682.5746 | 7023292.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.5.2 | Completion of installation / commissioning | 8361062.5381 | 0 | 0 | 0 | 0 | 0 | 0 | 8361062.5381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.5.3 | Final acceptance | 1672212.5076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1672212.5076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.6 | Segment Suzano km 36+940 / Estudantes km 50+770 (Extension of 13.830m in double track) | 105121359.0015 | 0 | 0 | 0 | 0 | 51509465.9107 | 22075485.3903 | 26280339.7504 | 5256067.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.6.1 | Auxiliary Vehicles and Equipment | 73584951.301 | 0 | 0 | 0 | 0 | 51509465.9107 | 22075485.3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.6.2 | Completion of installation / commissioning | 26280339.7504 | 0 | 0 | 0 | 0 | 0 | 0 | 26280339.7504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.6.3 | Final acceptance | 5256067.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5256067.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.7 | Segment Brás - km 2+240/ SE Engenheiro Gualberto - km 8+500 (extension of 6.260 m com 4 vias) - L11 | 95164093.6152 | 0 | 0 | 0 | 0 | 0 | 66614865.5306 | 23791023.4038 | 4758204.6808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.7.1 | Auxiliary Vehicles and Equipment | 66614865.5306 | 0 | 0 | 0 | 0 | 0 | 66614865.5306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.7.2 | Completion of installation / commissioning | 23791023.4038 | 0 | 0 | 0 | 0 | 0 | 0 | 23791023.4038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.7.3 | Final acceptance | 4758204.6808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4758204.6808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.8 | Segment Estudante - Cezar of Souza | 120300338.553 | 0 | 0 | 0 | 84210236.9871 | 36090101.5659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.8.1 | Auxiliary Vehicles and Equipment | 84210236.9871 | 0 | 0 | 0 | 84210236.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.8.2 | Completion of installation / commissioning | 30075084.6383 | 0 | 0 | 0 | 0 | 30075084.6383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.8.3 | Final acceptance | 6015016.9277 | 0 | 0 | 0 | 0 | 6015016.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.9 | Sebastião Gualberto - USP Leste | 66128403.7102 | 0 | 0 | 0 | 46289882.5972 | 19838521.1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.9.1 | Auxiliary Vehicles and Equipment | 46289882.5972 | 0 | 0 | 0 | 46289882.5972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.9.2 | Completion of installation / commissioning | 16532100.9276 | 0 | 0 | 0 | 0 | 16532100.9276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.9.3 | Final acceptance | 3306420.1855 | 0 | 0 | 0 | 0 | 3306420.1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.10 | USP Leste - Eng Manoel Feio | 121235406.8021 | 0 | 0 | 0 | 0 | 0 | 84864784.7615 | 30308851.7005 | 6061770.3401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.10.1 | Auxiliary Vehicles and Equipment | 84864784.7615 | 0 | 0 | 0 | 0 | 0 | 84864784.7615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.10.2 | Completion of installation / commissioning | 30308851.7005 | 0 | 0 | 0 | 0 | 0 | 0 | 30308851.7005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.10.3 | Final acceptance | 6061770.3401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6061770.3401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.11 | USP Leste - Eng Manoel Feio - Calmon Viana | 60731717.8902 | 0 | 0 | 0 | 42512202.5232 | 18219515.3671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.11.1 | Auxiliary Vehicles and Equipment | 42512202.5232 | 0 | 0 | 0 | 42512202.5232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.11.2 | Completion of installation / commissioning | 15182929.4726 | 0 | 0 | 0 | 0 | 15182929.4726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.11.3 | Final acceptance | 3036585.8945 | 0 | 0 | 0 | 0 | 3036585.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.12 | Segment Calmon Viana - Suzano - 3,95 km | 19035462.5373 | 0 | 0 | 0 | 0 | 13324823.7761 | 4758865.6343 | 951773.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.12.1 | Auxiliary Vehicles and Equipment | 13324823.7761 | 0 | 0 | 0 | 0 | 13324823.7761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.12.2 | Completion of installation / commissioning | 4758865.6343 | 0 | 0 | 0 | 0 | 0 | 4758865.6343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.12.3 | Final acceptance | 951773.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 951773.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.13 | Segment Airport of Guarulhos - Bonsucesso - 11 km | 36352445.8177 | 0 | 0 | 0 | 0 | 0 | 0 | 25446712.0724 | 10905733.7453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.13.1 | Auxiliary Vehicles and Equipment | 25446712.0724 | 0 | 0 | 0 | 0 | 0 | 0 | 25446712.0724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.13.2 | Completion of installation / commissioning | 9088111.4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9088111.4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.13.3 | Final acceptance | 1817622.2909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1817622.2909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.14 | Segment Engenheiro Goulart - Gabriela Mistral - 5,5 km | 18176222.9089 | 0 | 0 | 12723356.0362 | 4544055.7272 | 908811.1454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.14.1 | Auxiliary Vehicles and Equipment | 12723356.0362 | 0 | 0 | 12723356.0362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.14.2 | Completion of installation / commissioning | 4544055.7272 | 0 | 0 | 0 | 4544055.7272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.14.3 | Final acceptance | 908811.1454 | 0 | 0 | 0 | 0 | 908811.1454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2. | Energy - Substation of Energy | 471164207.3969 | 45482083.3739 | 157068410.1183 | 69104604.2869 | 12115480.0267 | 155716519.4025 | 31677110.1886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.1.1 | SE Sebastião Gualberto | 67424053.7272 | 0 | 44499875.46 | 22924178.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.2.1 | SE Dom Bosco | 19561630.162 | 0 | 0 | 0 | 0 | 9780815.081 | 9780815.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.3.1 | SE Guaianases | 19561630.162 | 0 | 0 | 0 | 0 | 9780815.081 | 9780815.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.4.1 | SE Ermelino Matarazzo | 68400728.6835 | 0 | 45144480.9311 | 23256247.7524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.5.1 | SE Calmon Viana | 67424053.7272 | 0 | 44499875.46 | 22924178.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.6.1 | SE São Miguel Paulista | 67424053.7272 | 44499875.46 | 22924178.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.7.1 | SE São João (Primary/ Rectifier 4MW) | 67424053.7272 | 0 | 0 | 0 | 0 | 67424053.7272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.8.1 | SE Presidente Dutra (4MW) | 44499875.46 | 0 | 0 | 0 | 0 | 44499875.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.9.1 | SE Braz Cubas | 24230960.0533 | 0 | 0 | 0 | 0 | 12115480.0267 | 12115480.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.10.1 | SE Engenheiro Manoel Feio | 24230960.0533 | 0 | 0 | 0 | 12115480.0267 | 12115480.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.11.1 | Spare parts | 982207.914 | 982207.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Signage | 2561324733.1902 | 39903891.556 | 51166999.6855 | 608376110.6536 | 440865931.5691 | 493875051.5575 | 453904747.0077 | 331126132.0012 | 142105869.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1 | Segment Barra Funda - km 4+452 (line 7) / Luz - km 0+000 (extension 4.452 m) | 72257325.646 | 0 | 50036931.6501 | 18667882.8582 | 0 | 0 | 0 | 0 | 3552511.1376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.1 | Auxiliary Vehicles and Equipment | 49735155.9268 | 0 | 49735155.9268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.2 | Completion of installation / commissioning | 17762555.6881 | 0 | 0 | 17762555.6881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.3 | Final acceptance | 3552511.1376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3552511.1376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.4 | CFTV | 1207102.8935 | 0 | 301775.7234 | 905327.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2 | Segment Luz - km 0+000 / Brás km 2+240 (extension of 2.240 m of double track) | 36533191.0428 | 0 | 0 | 196162.8233 | 25318222.0597 | 9231379.1723 | 0 | 0 | 1787426.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.1 | Auxiliary Vehicles and Equipment | 25023977.8248 | 0 | 0 | 0 | 25023977.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.2 | Completion of installation / commissioning | 8937134.9374 | 0 | 0 | 0 | 0 | 8937134.9374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.3 | Final acceptance | 1787426.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787426.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2.4 | CFTV | 784651.2931 | 0 | 0 | 196162.8233 | 294244.2349 | 294244.2349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3 | Segment Engenheiro Gualberto - km 8+500 / Corinthians Itaquera - km 19+450 (extension 10.950 m of double track) | 178037603.5859 | 428654.0935 | 0 | 714010.7817 | 123398050.6285 | 44759242.7639 | 0 | 0 | 8737645.3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.1.1 | Auxiliary Vehicles and Equipment | 122327034.456 | 0 | 0 | 0 | 122327034.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.2.1 | Completion of installation / commissioning | 43688226.5914 | 0 | 0 | 0 | 0 | 43688226.5914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.3.1 | Final acceptance | 8737645.3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8737645.3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.4.1 | Lane closure | 428654.0935 | 428654.0935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.5.1 | CFTV | 2856043.1266 | 0 | 0 | 714010.7817 | 1071016.1725 | 1071016.1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.4 | Segment Túnel 3 km 23+040 / Guaianazes km 24+800 -(Extension of 1760m of double track) | 28613865.6887 | 0 | 0 | 131431.8285 | 19858844.6051 | 7219182.3364 | 0 | 0 | 1404406.9187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.5.1.1 | Auxiliary Vehicles and Equipment | 19661696.8623 | 0 | 0 | 0 | 19661696.8623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.5.2.1 | Completion of installation / commissioning | 7022034.5937 | 0 | 0 | 0 | 0 | 7022034.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.5.3.1 | Final acceptance | 1404406.9187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404406.9187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.5.4.1 | CFTV | 525727.3139 | 0 | 0 | 131431.8285 | 197147.7427 | 197147.7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.5 | Segment Guaianazes km 24+800 / Suzano km 36+940 (Extension of 12.140m in double track. Railway TR 68 of km 25+000 to km 33+800 - Extension of 8.800m) | 144944367.5661 | 2165480.524 | 0 | 0 | 584548.7921 | 69400487.8102 | 30077094.0856 | 35694721.7605 | 7022034.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.5.1 | Auxiliary Vehicles and Equipment | 98308484.3117 | 0 | 0 | 0 | 0 | 68815939.0182 | 29492545.2935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.5.2 | Completion of installation / commissioning | 35110172.9685 | 0 | 0 | 0 | 0 | 0 | 0 | 35110172.9685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.5.3 | Final acceptance | 7022034.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7022034.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.5.4 | Lane closure | 2165480.524 | 2165480.524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.5.5 | CFTV | 2338195.1683 | 0 | 0 | 0 | 584548.7921 | 584548.7921 | 584548.7921 | 584548.7921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.6 | Segment Suzano km 36+940 / Estudantes km 50+770 (Extension of 13.830m in double track) | 225047746.4643 | 699616.7847 | 0 | 0 | 908203.7661 | 109058707.9276 | 47258419.8353 | 56087032.4199 | 11035765.7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.6.1.1.2 | Auxiliary Vehicles and Equipment | 154500720.2308 | 0 | 0 | 0 | 0 | 108150504.1615 | 46350216.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.6.2.1.2 | Completion of installation / commissioning | 55178828.6538 | 0 | 0 | 0 | 0 | 0 | 0 | 55178828.6538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.6.3.1.2 | Final acceptance | 11035765.7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11035765.7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.6.4.1.2 | Lane closure | 699616.7847 | 699616.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.6.5.1.2 | CFTV | 3632815.0642 | 0 | 0 | 0 | 908203.7661 | 908203.7661 | 908203.7661 | 908203.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.7 | Segment Brás - km 2+240/ SE Engenheiro Gualberto - km 8+500 (extension of 6.260 m com 4 vias) - L11 | 203449496.9494 | 0 | 0 | 0 | 910173.6049 | 910173.6049 | 140776335.3757 | 50862374.2373 | 9990440.1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.7.1 | Auxiliary Vehicles and Equipment | 139866161.7707 | 0 | 0 | 0 | 0 | 0 | 139866161.7707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.7.2 | Completion of installation / commissioning | 49952200.6324 | 0 | 0 | 0 | 0 | 0 | 0 | 49952200.6324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.7.3 | Final acceptance | 9990440.1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9990440.1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.7.4 | CFTV | 3640694.4197 | 0 | 0 | 0 | 910173.6049 | 910173.6049 | 910173.6049 | 910173.6049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.8 | Construction of New Line Estudantes - Cezar of Souza - 4,26 km | 90748616.5243 | 0 | 0 | 3285830.6606 | 60238200.9064 | 23234792.5745 | 0 | 0 | 3989792.3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.8.1.1.2 | Auxiliary Vehicles and Equipment | 55857093.3589 | 0 | 0 | 0 | 55857093.3589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.8.2.1.2 | Completion of installation / commissioning | 19948961.9139 | 0 | 0 | 0 | 0 | 19948961.9139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.8.3.1.2 | Final acceptance | 3989792.3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3989792.3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.8.4.1.2 | Lane closure | 9650269.6173 | 0 | 0 | 2895080.8852 | 3860107.8469 | 2895080.8852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.8.5.1.2 | CFTV | 1302499.2515 | 0 | 0 | 390749.7754 | 520999.7006 | 390749.7754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.9 | Segment SE Engenheiro Gualberto km 8+500 / USP Leste km 17+200 (Extension of 8.700 m in double track) | 141371755.5706 | 94392.7408 | 562031.7744 | 584548.7921 | 97775891.2366 | 35412652.2807 | 0 | 0 | 6942238.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.9.1 | Auxiliary Vehicles and Equipment | 97191342.4445 | 0 | 0 | 0 | 97191342.4445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.9.2 | Completion of installation / commissioning | 34711193.7302 | 0 | 0 | 0 | 0 | 34711193.7302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.9.3 | Final acceptance | 6942238.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6942238.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.9.4 | Lane closure | 188785.4816 | 94392.7408 | 94392.7408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.9.5 | CFTV | 2338195.1683 | 0 | 467639.0337 | 584548.7921 | 584548.7921 | 701458.5505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.10 | Segment USP Leste km 17+200 / Engenheiro Manoel Feio km 33+150 (Extension of 15.950m of double track) | 259054777.9505 | 177680.4533 | 177680.4533 | 0 | 830132.6045 | 1037665.7557 | 179221793.5706 | 64882387.4121 | 12727437.7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.10.1.1.2 | Auxiliary Vehicles and Equipment | 178184127.8149 | 0 | 0 | 0 | 0 | 0 | 178184127.8149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.10.2.1.2 | Completion of installation / commissioning | 63637188.5053 | 0 | 0 | 0 | 0 | 0 | 0 | 63637188.5053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.10.3.1.2 | Final acceptance | 12727437.7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12727437.7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.10.4.1.2 | Lane closure | 355360.9065 | 177680.4533 | 177680.4533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.10.5.1.2 | CFTV | 4150663.0226 | 0 | 0 | 0 | 830132.6045 | 1037665.7557 | 1037665.7557 | 1245198.9068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.11 | Segment Engenheiro Manoel Feio km 33+150 / Calmon Viana km 40+140 ( Extension of 7.990 m of double track) | 129593035.7427 | 0 | 0 | 727744.9162 | 89987380.1037 | 32502222.4951 | 0 | 0 | 6375688.2277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.11.1 | Auxiliary Vehicles and Equipment | 89259635.1875 | 0 | 0 | 0 | 89259635.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.11.2 | Completion of installation / commissioning | 31878441.1384 | 0 | 0 | 0 | 0 | 31878441.1384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.11.3 | Final acceptance | 6375688.2277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375688.2277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.11.4 | CFTV | 2079271.1891 | 0 | 0 | 727744.9162 | 727744.9162 | 623781.3567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.12 | Construction of New Line Calmon Viana - Suzano - 3,95 km | 71543270.3937 | 0 | 0 | 7184804.6331 | 521787.6361 | 44685674.6871 | 15959169.5311 | 0 | 3191833.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.12.1 | Auxiliary Vehicles and Equipment | 44685674.6871 | 0 | 0 | 0 | 0 | 44685674.6871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.12.2 | Completion of installation / commissioning | 15959169.5311 | 0 | 0 | 0 | 0 | 0 | 15959169.5311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.12.3 | Final acceptance | 3191833.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191833.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.12.4 | Lane closure | 6663016.997 | 0 | 0 | 6663016.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.12.5 | CFTV | 1043575.2723 | 0 | 0 | 521787.6361 | 521787.6361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.13 | Segment Eng Goulart - Guarulhos Airport | 159591695.3112 | 0 | 0 | 0 | 0 | 111714186.7178 | 39897923.8278 | 0 | 7979584.7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.13.1 | Auxiliary Vehicles and Equipment | 111714186.7178 | 0 | 0 | 0 | 0 | 111714186.7178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.13.2 | Completion of installation / commissioning | 39897923.8278 | 0 | 0 | 0 | 0 | 0 | 39897923.8278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.13.3 | Final acceptance | 7979584.7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7979584.7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.14 | Construction of New Line Guarulhos Airport - Bonsucesso - 11 km | 182401580.6184 | 0 | 0 | 0 | 0 | 4708683.4311 | 714010.7817 | 123599616.1713 | 53379270.2344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.14.1.1.2.1 | Auxiliary Vehicles and Equipment | 122885605.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 122885605.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.14.2.0.2.1 | Completion of installation / commissioning | 43887716.2106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43887716.2106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.14.2.1.2.1 | Final acceptance | 8777543.2421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8777543.2421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.14.3.1.2.1 | Lane closure | 3994672.6495 | 0 | 0 | 0 | 0 | 3994672.6495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.14.4.1.2.1 | CFTV | 2856043.1266 | 0 | 0 | 0 | 0 | 714010.7817 | 714010.7817 | 714010.7817 | 714010.7817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.15 | Construction of New Line Engenheiro Goulart - Gabriela Mistral - 5,5 km | 81357270.8863 | 0 | 390355.8077 | 56442627.0704 | 20534495.6254 | 0 | 0 | 0 | 3989792.3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.15.1 | Auxiliary Vehicles and Equipment | 55857093.3589 | 0 | 0 | 55857093.3589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.15.2 | Completion of installation / commissioning | 19948961.9139 | 0 | 0 | 0 | 19948961.9139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.15.3 | Final acceptance | 3989792.3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3989792.3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.15.4 | CFTV | 1561423.2307 | 0 | 390355.8077 | 585533.7115 | 585533.7115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.17 | Onboard Equipment for Trains (including demobilization) | 475575457.1267 | 0 | 0 | 475575457.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.18 | Onboard Equipment - MRS (including demobilization) | 13459682.7489 | 0 | 0 | 13459682.7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.19 | Onboard Equipment for Auxiliary Vehicles | 31405926.414 | 0 | 0 | 31405926.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.20 | Track equipment replacement | 36338066.9598 | 36338066.9598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | CCO | 235887028.5569 | 0 | 165120919.9898 | 58971757.1392 | 0 | 0 | 0 | 11794351.4278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1 | CCO Line 11 | 90856332.7156 | 0 | 63599432.9009 | 22714083.1789 | 0 | 0 | 0 | 4542816.6358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1.1 | Auxiliary Vehicles and Equipment | 63599432.9009 | 0 | 63599432.9009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1.2 | Completion of installation / commissioning | 22714083.1789 | 0 | 0 | 22714083.1789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1.3 | Final acceptance | 4542816.6358 | 0 | 0 | 0 | 0 | 0 | 0 | 4542816.6358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.2 | CCO Line 12 | 73032675.0019 | 0 | 51122872.5013 | 18258168.7505 | 0 | 0 | 0 | 3651633.7501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.2.1 | Auxiliary Vehicles and Equipment | 51122872.5013 | 0 | 51122872.5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.2.2 | Completion of installation / commissioning | 18258168.7505 | 0 | 0 | 18258168.7505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.2.3 | Final acceptance | 3651633.7501 | 0 | 0 | 0 | 0 | 0 | 0 | 3651633.7501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.3 | CCO Line 13 | 71998020.8393 | 0 | 50398614.5875 | 17999505.2098 | 0 | 0 | 0 | 3599901.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.3.1 | Auxiliary Vehicles and Equipment | 50398614.5875 | 0 | 50398614.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.3.2 | Completion of installation / commissioning | 17999505.2098 | 0 | 0 | 17999505.2098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.3.3 | Final acceptance | 3599901.042 | 0 | 0 | 0 | 0 | 0 | 0 | 3599901.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Yards | 995639062.3939 | 75580544.1978 | 127712572.945 | 190361602.8016 | 115607646.8394 | 223498632.6429 | 106877958.7359 | 106877958.7359 | 49122145.4955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Luz Complex | 227212806.255 | 22721280.6255 | 0 | 0 | 0 | 0 | 102245762.8147 | 102245762.8147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | Civil Construction | 163989057.3567 | 16398905.7357 | 0 | 0 | 0 | 0 | 73795075.8105 | 73795075.8105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2 | Overhead Network | 23189226.1631 | 2318922.6163 | 0 | 0 | 0 | 0 | 10435151.7734 | 10435151.7734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3 | Permanent Track | 39114224.1928 | 3911422.4193 | 0 | 0 | 0 | 0 | 17601400.8868 | 17601400.8868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4 | CFTV | 920298.5424 | 92029.8542 | 0 | 0 | 0 | 0 | 414134.3441 | 414134.3441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Braz Cubas Washer | 92511935.0992 | 46255967.5496 | 46255967.5496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1 | Civil Construction | 70230238.3735 | 35115119.1868 | 35115119.1868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2 | Overhead Network | 7950671.9259 | 3975335.963 | 3975335.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.3 | Permanent Track | 13410726.2574 | 6705363.1287 | 6705363.1287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.4 | CFTV | 920298.5424 | 460149.2712 | 460149.2712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Engenheiro São Paulo Shelter | 232135592.2212 | 460149.2712 | 0 | 0 | 115607646.8394 | 116067796.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.1 | Civil Construction | 154042463.8598 | 0 | 0 | 0 | 77021231.9299 | 77021231.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.2 | Overhead Network | 28723581.0231 | 0 | 0 | 0 | 14361790.5116 | 14361790.5116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.3 | Permanent Track | 48449248.7959 | 0 | 0 | 0 | 24224624.3979 | 24224624.3979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.4 | CFTV | 920298.5424 | 460149.2712 | 0 | 0 | 0 | 460149.2712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Calmon Viana Base | 107357431.0657 | 0 | 53678715.5329 | 53678715.5329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.1 | Civil Construction | 92823328.3559 | 0 | 46411664.178 | 46411664.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.2 | Overhead Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.3 | Permanent Track | 11773207.0826 | 0 | 5886603.5413 | 5886603.5413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.4 | CFTV | 2760895.6272 | 0 | 1380447.8136 | 1380447.8136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | Railway yard TLS - Jundiapeba | 30715733.7574 | 6143146.7515 | 3071573.3757 | 21501013.6302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.1 | Civil Construction | 19164252.3007 | 3832850.4601 | 1916425.2301 | 13414976.6105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.2 | Overhead Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.3 | Permanent Track | 10631182.9143 | 2126236.5829 | 1063118.2914 | 7441828.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.4 | CFTV | 920298.5424 | 184059.7085 | 92029.8542 | 644208.9797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | Mogi das Cruzes Base | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6.4 | CFTV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7 | Artur Alvim Base | 21931956.843 | 0 | 0 | 21931956.843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7.1 | Civil Construction | 17888867.3507 | 0 | 0 | 17888867.3507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7.2 | Overhead Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7.3 | Permanent Track | 3122790.9499 | 0 | 0 | 3122790.9499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7.4 | CFTV | 920298.5424 | 0 | 0 | 920298.5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9 | Guaianases Yard | 16111700.4396 | 0 | 16111700.4396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9.1 | Civil Construction | 15191401.8972 | 0 | 15191401.8972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9.2 | Overhead Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9.3 | Permanent Track | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9.4 | CFTV | 920298.5424 | 0 | 920298.5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.10 | Via of teste | 9426964.6425 | 0 | 0 | 9426964.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.10.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.10.2 | Overhead Network | 3508698.3767 | 0 | 0 | 3508698.3767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.10.3 | Permanent Track | 5918266.2658 | 0 | 0 | 5918266.2658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.10.4 | CFTV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.11 | Cezar of Souza Yard | 93534248.7689 | 0 | 0 | 0 | 0 | 93534248.7689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.11.1 | Civil Construction | 17002602.275 | 0 | 0 | 0 | 0 | 17002602.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.11.2 | Overhead Network | 12175296.954 | 0 | 0 | 0 | 0 | 12175296.954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.11.3 | Permanent Track | 63436050.9974 | 0 | 0 | 0 | 0 | 63436050.9974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.11.4 | CFTV | 920298.5424 | 0 | 0 | 0 | 0 | 920298.5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.12 | Roosevelt Complex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.12.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.12.2 | Overhead Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.12.3 | Permanent Track | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.12.4 | CFTV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.13 | Itaim Paulista Yard | 23160979.6057 | 0 | 0 | 0 | 0 | 13896587.7634 | 4632195.9211 | 4632195.9211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.13.1 | Civil Construction | 10758166.7805 | 0 | 0 | 0 | 0 | 6454900.0683 | 2151633.3561 | 2151633.3561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.13.2 | Overhead Network | 4273770.0577 | 0 | 0 | 0 | 0 | 2564262.0346 | 854754.0115 | 854754.0115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.13.3 | Permanent Track | 7208744.2251 | 0 | 0 | 0 | 0 | 4325246.535 | 1441748.845 | 1441748.845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.13.4 | CFTV | 920298.5424 | 0 | 0 | 0 | 0 | 552179.1254 | 184059.7085 | 184059.7085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.14 | Comendador Ermelino Base | 38371587.5243 | 0 | 7674317.5049 | 30697270.0194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.14.1 | Civil Construction | 34432801.5566 | 0 | 6886560.3113 | 27546241.2453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.14.2 | Overhead Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.14.3 | Permanent Track | 3018487.4253 | 0 | 603697.4851 | 2414789.9402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.14.4 | CFTV | 920298.5424 | 0 | 184059.7085 | 736238.8339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15 | Engenheiro Manoel Feio Yard | 53125682.1336 | 0 | 0 | 53125682.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15.1 | Civil Construction | 14428774.168 | 0 | 0 | 14428774.168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15.2 | Overhead Network | 14060382.4441 | 0 | 0 | 14060382.4441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15.3 | Permanent Track | 23716226.9791 | 0 | 0 | 23716226.9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15.4 | CFTV | 920298.5424 | 0 | 0 | 920298.5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16 | Eng Goulart Parking Yard | 920298.5424 | 0 | 920298.5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16.1 | Civil Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16.2 | Overhead Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16.3 | Permanent Track | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16.4 | CFTV | 920298.5424 | 0 | 920298.5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16 | Bom Sucesso Parking Yard | 49122145.4955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49122145.4955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.17.1 | Civil Construction | 49122145.4955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49122145.4955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Other Ventures | 3267733225.742 | 8620661.2458 | 269421513.2969 | 699174673.0355 | 894627886.3634 | 716722757.7933 | 286404437.716 | 258439140.6253 | 28698593.6542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31687068.6035 | 73936493.4081 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Transpositions and Crossings | 1245442598.6785 | 731778.25 | 32410151.3309 | 326159348.9132 | 515790432.2757 | 338972635.1542 | 25440642.5771 | 5937610.1773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 | OAES | 857680925.6678 | 0 | 3566023.3152 | 226549928.6133 | 367885291.963 | 250864633.8115 | 8815047.9648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.1 | OAES in the km 32+205 | 5371883.2371 | 0 | 0 | 2685941.6186 | 2685941.6186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.2 | OAES in the km 34+720 | 6886329.4554 | 0 | 0 | 0 | 0 | 3443164.7277 | 3443164.7277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.3 | Railway bridge in the km 37+530 | 5371883.2371 | 0 | 0 | 0 | 0 | 2685941.6186 | 2685941.6186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.4 | Railway bridge in the km 50+770 | 5371883.2371 | 0 | 0 | 0 | 0 | 2685941.6186 | 2685941.6186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.5 | Railway bridge Cezar of Souza | 18193017.5736 | 0 | 0 | 0 | 9096508.7868 | 9096508.7868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.6 | OAE in the km 31+850 | 15632919.6502 | 0 | 0 | 0 | 7816459.8251 | 7816459.8251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.7 | Construction of Via Corrida Line 13 | 786588916.0166 | 0 | 0 | 218514952.022 | 342937346.7598 | 225136617.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.8 | Railway bridge - 5 m - Line 13 expansion 2 | 14264093.2606 | 0 | 3566023.3152 | 5349034.9727 | 5349034.9727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2 | Footbridge | 190820357.819 | 0 | 21862035.8839 | 81956618.3656 | 73408058.5861 | 13593644.9834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.1 | Segment between station Palmeiras - Barra Funda and station Guaianases | 27027283.7959 | 0 | 13453560.5439 | 13573723.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.1.1 | Civil Construction | 26907121.0878 | 0 | 13453560.5439 | 13453560.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.1.2 | CFTV | 120162.7081 | 0 | 0 | 120162.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.2 | Segment between station Guaianases and station Antônio Gianetti Neto | 16957035.1194 | 0 | 8408475.3399 | 8548559.7795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.2.1 | Civil Construction | 16816950.6799 | 0 | 8408475.3399 | 8408475.3399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.2.2 | CFTV | 140084.4395 | 0 | 0 | 140084.4395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.3 | Segment between station Antônio Gianetti Neto and station Calmon Viana | 31820195.5457 | 0 | 0 | 15850016.4188 | 15970179.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.3.1 | Civil Construction | 31700032.8376 | 0 | 0 | 15850016.4188 | 15850016.4188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.3.2 | CFTV | 120162.7081 | 0 | 0 | 0 | 120162.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.4 | Segment between station Calmon Viana and station Estudantes | 27047205.5273 | 0 | 0 | 0 | 13453560.5439 | 13593644.9834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.4.1 | Civil Construction | 26907121.0878 | 0 | 0 | 0 | 13453560.5439 | 13453560.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.4.2 | CFTV | 140084.4395 | 0 | 0 | 0 | 0 | 140084.4395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.5 | Segment between station Brás and station USP Leste | 20300503.524 | 0 | 0 | 10150251.762 | 10150251.762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.5.1 | Civil Construction | 20180340.8159 | 0 | 0 | 10090170.4079 | 10090170.4079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.5.2 | CFTV | 120162.7081 | 0 | 0 | 60081.3541 | 60081.3541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.6 | Segment between station USP Leste and station Itaim Paulista | 23683815.3914 | 0 | 0 | 11841907.6957 | 11841907.6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.6.1 | Civil Construction | 23543730.9518 | 0 | 0 | 11771865.4759 | 11771865.4759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.6.2 | CFTV | 140084.4395 | 0 | 0 | 70042.2198 | 70042.2198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.7 | Segment between station Itaim Paulista and station Engenheiro Manoel Feio | 20300503.524 | 0 | 0 | 10150251.762 | 10150251.762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1..2.7.1 | Civil Construction | 20180340.8159 | 0 | 0 | 10090170.4079 | 10090170.4079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1..2.7.2 | CFTV | 120162.7081 | 0 | 0 | 60081.3541 | 60081.3541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.8 | Segment between station Engenheiro Manoel Feio and station Calmon Viana | 23683815.3914 | 0 | 0 | 11841907.6957 | 11841907.6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.8.1 | Civil Construction | 23543730.9518 | 0 | 0 | 11771865.4759 | 11771865.4759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.8.2 | CFTV | 140084.4395 | 0 | 0 | 70042.2198 | 70042.2198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3 | Viaducts | 92357571.0136 | 0 | 0 | 0 | 29553190.8945 | 40241175.3295 | 16625594.6123 | 5937610.1773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3.1 | Access ramp to viaduct Argeu Batalha | 11875220.3546 | 0 | 0 | 0 | 0 | 0 | 5937610.1773 | 5937610.1773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3.2 | Viaduct between station Braz Cubas and station Mogi das Cruzes | 34856582.0564 | 0 | 0 | 0 | 17428291.0282 | 17428291.0282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3.3 | Viaducts between station Estudantes and Cezar of Souza (extension of Line 11-Coral) | 24249799.7325 | 0 | 0 | 0 | 12124899.8663 | 12124899.8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3.4 | Viaduct Campos Salles | 21375968.87 | 0 | 0 | 0 | 0 | 10687984.435 | 10687984.435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4 | Underpasses | 104583744.1782 | 731778.25 | 6982092.1319 | 17652801.9343 | 44943890.8321 | 34273181.0298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.1 | Underpass 155 | 3658891.25 | 0 | 1829445.625 | 1829445.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.2 | Underpass 040 | 3658891.25 | 0 | 1829445.625 | 1829445.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.3 | Underpass 156 | 3658891.25 | 0 | 1829445.625 | 1829445.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.4 | Tunnel of station Jundiapeba | 3658891.25 | 731778.25 | 1463556.5 | 1463556.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.5 | CFTV | 60397.5139 | 0 | 30198.7569 | 30198.7569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.6 | Raising and widening of lower way 137 | 21341419.6047 | 0 | 0 | 10670709.8024 | 10670709.8024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.7 | Targeted improvements on the lower way 119 | 21326641.7913 | 0 | 0 | 0 | 10663320.8957 | 10663320.8957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.8 | Raising and widening of lower way 118 | 21991643.3958 | 0 | 0 | 0 | 10995821.6979 | 10995821.6979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.9 | Raising and widening of lower way 154 | 3136192.5 | 0 | 0 | 0 | 1568096.25 | 1568096.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.10 | Raising and widening of lower way 88 | 21991643.3958 | 0 | 0 | 0 | 10995821.6979 | 10995821.6979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.11 | CFTV | 100240.9767 | 0 | 0 | 0 | 50120.4883 | 50120.4883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Permanent Track | 1544717379.2117 | 0 | 54612356.7619 | 191353526.4818 | 378837454.0877 | 377750122.6391 | 260963795.1389 | 252501530.448 | 28698593.6542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1 | Recovery of the infrastructure and superstructure of the permanent way, Lines 11 and 12, with an extension of 89.570m of double track, excluding the parking yards. It also includes 135 sets of AMVs, excluding the Barra Funda-Luz and Luz-Brás segments | 64234209.1908 | 0 | 16058552.2977 | 48175656.8931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1.1 | Permanent Track | 64234209.1908 | 0 | 16058552.2977 | 48175656.8931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1.2 | Seal strip | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3 | Segment Luz - km 0+000 / Brás km 2+240 (extension of 2.240 m of double track) | 47250653.4981 | 0 | 0 | 11812663.3745 | 17718995.0618 | 17718995.0618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.1 | Permanent Track | 47250653.4981 | 0 | 0 | 11812663.3745 | 17718995.0618 | 17718995.0618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4 | Segment Engenheiro Gualberto - km 8+500 / Corinthians Itaquera - km 19+450 (extension 10.950 m of double track) | 78504610.9525 | 0 | 0 | 19626152.7381 | 29439229.1072 | 29439229.1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.1 | Permanent Track | 141504.5932 | 0 | 0 | 35376.1483 | 53064.2224 | 53064.2224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.2 | Seal strip | 78363106.3594 | 0 | 0 | 19590776.5898 | 29386164.8848 | 29386164.8848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.5 | Segment Túnel 3 km 23+040 / Guaianazes km 24+800 -(Extension of 1760m of double track) | 4568025.6696 | 0 | 0 | 1142006.4174 | 1713009.6261 | 1713009.6261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.5.1 | Permanent Track | 4568025.6696 | 0 | 0 | 1142006.4174 | 1713009.6261 | 1713009.6261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.6 | Segment Guaianazes km 24+800 / Suzano km 36+940 (Extension of 12.140m in double track. Railway TR 68 of km 25+000 to km 33+800 - Extension of 8.800m) | 238380666.2867 | 0 | 0 | 0 | 59595166.5717 | 59595166.5717 | 59595166.5717 | 59595166.5717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.6.1 | Permanent Track | 39585238.9185 | 0 | 0 | 0 | 9896309.7296 | 9896309.7296 | 9896309.7296 | 9896309.7296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.6.2 | Seal strip | 198795427.3682 | 0 | 0 | 0 | 49698856.8421 | 49698856.8421 | 49698856.8421 | 49698856.8421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.7 | Segment Suzano km 36+940 / Estudantes km 50+770 (Extension of 13.830m in double track) | 169921583.6687 | 0 | 0 | 0 | 42480395.9172 | 42480395.9172 | 42480395.9172 | 42480395.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.7.1 | Permanent Track | 2409796.8584 | 0 | 0 | 0 | 602449.2146 | 602449.2146 | 602449.2146 | 602449.2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.7.2 | Seal strip | 167511786.8103 | 0 | 0 | 0 | 41877946.7026 | 41877946.7026 | 41877946.7026 | 41877946.7026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.8 | Segment Brás - km 2+240/ SE Engenheiro Gualberto - km 8+500 (extension of 6.260 m com 4 vias) | 349635289.101 | 0 | 0 | 0 | 87408822.2752 | 87408822.2752 | 87408822.2752 | 87408822.2752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.8.1 | Permanent Track | 349635289.101 | 0 | 0 | 0 | 87408822.2752 | 87408822.2752 | 87408822.2752 | 87408822.2752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.9 | Construction of New Line Estudantes - Cezar of Souza - 4,26 km | 70057537.8347 | 0 | 0 | 21017261.3504 | 28023015.1339 | 21017261.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.9.1 | Permanent Track | 59336195.3615 | 0 | 0 | 17800858.6085 | 23734478.1446 | 17800858.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.9.2 | Seal strip | 10721342.4732 | 0 | 0 | 3216402.742 | 4288536.9893 | 3216402.742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.10 | Segment SE Engenheiro Gualberto km 8+500 / USP Leste km 17+200 (Extension of 8.700 m in double track) | 92867705.2445 | 0 | 18573541.0489 | 23216926.3111 | 23216926.3111 | 27860311.5734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.10.1 | Permanent Track | 2821718.5283 | 0 | 564343.7057 | 705429.6321 | 705429.6321 | 846515.5585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.10.2 | Seal strip | 90045986.7162 | 0 | 18009197.3432 | 22511496.6791 | 22511496.6791 | 27013796.0149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.11 | Segment USP Leste km 17+200 / Engenheiro Manoel Feio km 33+150 (Extension of 15.950m of double track) | 114395173.4323 | 0 | 0 | 0 | 22879034.6865 | 28598793.3581 | 28598793.3581 | 34318552.0297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.11.1 | Permanent Track | 33708808.1079 | 0 | 0 | 0 | 6741761.6216 | 8427202.027 | 8427202.027 | 10112642.4324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.11.2 | Seal strip | 80686365.3244 | 0 | 0 | 0 | 16137273.0649 | 20171591.3311 | 20171591.3311 | 24205909.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.12 | Segment Engenheiro Manoel Feio km 33+150 / Calmon Viana km 40+140 ( Extension of 7.990 m of double track) | 63458402.6045 | 0 | 0 | 22210440.9116 | 22210440.9116 | 19037520.7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.11.1 | Permanent Track | 1611680.8545 | 0 | 0 | 564088.2991 | 564088.2991 | 483504.2564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.11.2 | Seal strip | 61846721.75 | 0 | 0 | 21646352.6125 | 21646352.6125 | 18554016.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.13 | Construction of New Line Calmon Viana - Suzano - 3,95 km | 56728093.4501 | 0 | 0 | 14182023.3625 | 14182023.3625 | 14182023.3625 | 14182023.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.13.1 | Permanent Track | 46786942.5653 | 0 | 0 | 11696735.6413 | 11696735.6413 | 11696735.6413 | 11696735.6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.13.2 | Seal strip | 9941150.8848 | 0 | 0 | 2485287.7212 | 2485287.7212 | 2485287.7212 | 2485287.7212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.14 | Construction of New Line Airport of Guarulhos - Bonsucesso - 11 km | 114794374.6169 | 0 | 0 | 0 | 0 | 28698593.6542 | 28698593.6542 | 28698593.6542 | 28698593.6542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.14.1 | Permanent Track | 87110156.9631 | 0 | 0 | 0 | 0 | 21777539.2408 | 21777539.2408 | 21777539.2408 | 21777539.2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.14.2 | Seal strip | 27684217.6538 | 0 | 0 | 0 | 0 | 6921054.4135 | 6921054.4135 | 6921054.4135 | 6921054.4135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.15 | Construction of New Line Engenheiro Goulart - Gabriela Mistral - 4,9 km | 79921053.6614 | 0 | 19980263.4153 | 29970395.123 | 29970395.123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.14.1 | Permanent Track | 66078944.8344 | 0 | 16519736.2086 | 24779604.3129 | 24779604.3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.14.2 | Seal strip | 13842108.8269 | 0 | 3460527.2067 | 5190790.8101 | 5190790.8101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Auxiliary Vehicles and Equipment | 477573247.8518 | 7888882.9958 | 182399005.204 | 181661797.6405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31687068.6035 | 73936493.4081 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1 | Acquisition of a Tamping Machine, Leveling Machine, and Track Aligner | 60463961.0749 | 0 | 9069594.1612 | 21162386.3762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9069594.1612 | 21162386.3762 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.2 | Acquisition of a Tamping Machine, Leveling Machine and Track aligner of AMVs | 64665372.3725 | 0 | 9699805.8559 | 22632880.3304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9699805.8559 | 22632880.3304 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.3 | Acquisition of a Ballast Regulator | 52592553.305 | 7888882.9958 | 18407393.6568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7888882.9958 | 18407393.6568 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.4 | Acquisition of Two Line Trucks Equipped with Munck-type Crane (5t capacity) and Two Trailers | 33525237.2706 | 0 | 16762618.6353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5028785.5906 | 11733833.0447 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.5 | Acquisition of a Road Truck, 12t capacity, Equipped with a Munck-type Crane for 5t | 18593248.3965 | 0 | 18593248.3965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.6 | Acquisition of a Set of Road-Rail Equipment for the Extrapolation/Positioning of Wooden/Concrete Sleepers | 3431458.3646 | 0 | 1029437.5094 | 2402020.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.7 | Acquisition of Control Car | 57739189.498 | 0 | 17321756.8494 | 40417432.6486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.8 | Acquisition of a Crawler Hydraulic Excavator | 1239549.8931 | 0 | 1239549.8931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.9 | Acquisition of a Tractor Unit (Truck) and Trailer | 991639.9145 | 0 | 991639.9145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.10 | Rail Grinder, minimum capacity of 500m/h, for 1600mm gauge | 44091407.2343 | 0 | 13227422.1703 | 30863985.064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.11 | Road-Rail Truck, 1600mm gauge, equipped with a 500kV generator set | 1285177.6255 | 0 | 1285177.6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.12 | Road-Rail Truck, 1600mm gauge, with a box equipped with equipment and tools for rail fitting of railway vehicles and emergency service | 1058193.7829 | 0 | 1058193.7829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.13 | Road-Rail Crane, 1600mm gauge, electronic slewing system, telescopic boom with a capacity of 150 tons | 18593248.3965 | 0 | 5577974.5189 | 13015273.8775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.14 | Three locomotives, 100t and 2000 hp | 26454844.5734 | 0 | 7936453.372 | 18518391.2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.15 | 20 Flatbed Wagons (14m in length for TLS) without crane | 19655657.8012 | 0 | 5896697.3404 | 13758960.4608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.16 | 4 Track Inspection Cars (14m in length) with crane | 3931131.5602 | 0 | 1179339.4681 | 2751792.0922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.17 | 10 Hopper Wagons for ballast unloading | 9827828.9006 | 0 | 2948348.6702 | 6879480.2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.18 | Control and Support Vehicle (CSV) with elevating platform and coil transport wagon | 13227420.7196 | 0 | 3968226.2159 | 9259194.5037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.19 | Locomotive Tractor Vehicles (for yard work) | 2204570.3811 | 0 | 2204570.3811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.20 | 2.5 Ton Forklift | 11728314.4275 | 0 | 11728314.4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.21 | 5 Ton Forklift | 1742580.612 | 0 | 1742580.612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.22 | Electric Pallet Trucks | 412646.1594 | 0 | 412646.1594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.23 | Aerial Work Platform | 1119313.5535 | 0 | 1119313.5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.23 | Mobile Welding Unit for Railways | 24592669.879 | 0 | 24592669.879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.23 | Chemical Weed Control Wagon | 1063315.0609 | 0 | 1063315.0609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.23 | Fuel Tank Wagon | 1222812.32 | 0 | 1222812.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.23 | Road-Rail Backhoe (+ Multi-task Implements) | 660680.093 | 0 | 660680.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.23 | Wheel Loader (With Bucket + Fork Attachment + Hydraulic Attachment for Concrete Sleepers) | 1459224.6813 | 0 | 1459224.6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Rolling Stock | 202062759.513 | 49186691.8233 | 54502684.0433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98373383.6465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1 | Trains | 202062759.513 | 49186691.8233 | 54502684.0433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98373383.6465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2.2 | CCTV Installation | 196746767.293 | 49186691.8233 | 49186691.8233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98373383.6465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2.3. | Visual Communication | 5315992.22 | 0 | 5315992.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Social and Environmental | 1901640760.8288 | 269080361.7833 | 152185331.5012 | 511832023.0229 | 686947656.9267 | 281450494.476 | 144893.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Environmental Liabilities | 234800720.4138 | 234800720.4138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.1.1 | Risk Management | 33184236.2 | 33184236.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.2.1 | Waste Containers | 196927500 | 196927500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.3.1 | Waterproofing | 2478778.264 | 2478778.264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.4.1 | Ballast Replacement | 2210205.9499 | 2210205.9499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.2 | Risk Management | 1370285.5395 | 1370285.5395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.3 | Disturbances and Vibrations | 90950 | 30316.6667 | 30316.6667 | 30316.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.3.1 | Sound Barrier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4 | Station's Expropriation | 1653726817.2735 | 25379589.2718 | 149063502.503 | 511175360.3335 | 686802763.808 | 281305601.3573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.1 | Expropriation in Bom Retiro | 493039140.0114 | 0 | 49303914.0011 | 221867613.0052 | 221867613.0052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.2 | Expropriation in Brás Cubas | 10866581.3346 | 1086658.1335 | 4889961.6006 | 4889961.6006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.3 | Expropriation in Estudantes | 16563932.0631 | 1656393.2063 | 7453769.4284 | 7453769.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.4 | Expropriation in Itaquaquecetuba | 1296685.275 | 129668.5275 | 583508.3738 | 583508.3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.5 | Expropriation in Jundiapeba | 5109119.3486 | 510911.9349 | 2299103.7069 | 2299103.7069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.6 | Expropriation in Lajeado | 65771600.5188 | 0 | 6577160.0519 | 29597220.2335 | 29597220.2335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.7 | Expropriation in Mogi das Cruzes | 62087775.3688 | 6208777.5369 | 27939498.916 | 27939498.916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.8 | Expropriation in Suzano | 648342.6375 | 324171.3188 | 324171.3188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.9 | Expropriation in Cangaíba | 342294064.9159 | 0 | 34229406.4916 | 154032329.2121 | 154032329.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.10 | Expropriation between Airport of Guarulhos - Jardim dos Eucaliptos | 30926017.228 | 15463008.614 | 15463008.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.11 | Expropriation between Jardim dos Eucaliptos and São João | 244843592.7282 | 0 | 0 | 24484359.2728 | 110179616.7277 | 110179616.7277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.12 | Expropriation in São João | 34395249.5385 | 0 | 0 | 3439524.9539 | 15477862.2923 | 15477862.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.13 | Expropriation between São João and Presidente Dutra | 173810485.6355 | 0 | 0 | 17381048.5636 | 78214718.536 | 78214718.536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.14 | Expropriation in Presidente Dutra | 58887767.799 | 0 | 0 | 5888776.7799 | 26499495.5095 | 26499495.5095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.15 | Expropriation in Presidente Dutra and Bonsucesso | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.16 | Expropriation in Bonsucesso | 6781343.3929 | 0 | 0 | 678134.3393 | 3051604.5268 | 3051604.5268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.17 | Expropriation in Bonsucesso and segment final of lote | 2993796.344 | 0 | 0 | 299379.6344 | 1347208.3548 | 1347208.3548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.18 | Expropriation in Jardim dos Eucaliptos | 56552595.3324 | 0 | 0 | 5655259.5332 | 25448667.8996 | 25448667.8996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4.19 | Expropriation between the stations Estudantes and César of Souza | 46858727.8011 | 0 | 0 | 4685872.7801 | 21086427.5105 | 21086427.5105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.5 | Biodiversity | 1904749.56 | 939676.8933 | 681739.3333 | 70833.3333 | 70833.3333 | 70833.3333 | 70833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.6 | Compliance with IFC Performance Standards and Concession Agreement Requirements | 4150000 | 4150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.7 | LP - Preliminary License in the Environmental Licensing Process | 3708520.6176 | 1854260.3088 | 1854260.3088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.8 | LI - Environmental Programs - PBA | 1444358.7121 | 481452.904 | 481452.904 | 481452.904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.9 | LO - Operating License | 444358.7121 | 74059.7854 | 74059.7854 | 74059.7854 | 74059.7854 | 74059.7854 | 74059.7854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Projects | 440876408.4746 | 178309215.3974 | 178309215.3974 | 42128988.8399 | 42128988.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1 | Projects Line 11 | 199757895.5951 | 99878947.7976 | 99878947.7976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.2 | Projects Line 12 | 117298672.5941 | 55830972.0973 | 55830972.0973 | 2818364.1997 | 2818364.1997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3 | Projects Line 13 | 123819840.2853 | 22599295.5025 | 22599295.5025 | 39310624.6402 | 39310624.6402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0