## Capa
GOVERNMENT OF THE STATE OF SÃO PAULO
State Secretariat for Investment Partnerships
SPI PROCESS nº 021.00000891/2024-87
INTERNATIONAL COMPETITION Nº 02/2024
PPP LOTE ALTO TIETÊ
EXHIBIT IX.A – MONETARY CONSIDERATION AND CONTRIBUTION
Note 1: The table below aims to exemplify the content of Annex IX of this document and assist in the interpretation of the contractual provisions applicable to it.
Note 2: For all purposes set forth in the AGREEMENT and EXHIBITS, references to EXHIBIT IX.A apply to the content of the table set forth in the "Exhibit IX" tab of this document, as well as to the notes set forth in this "Cover" tab.
Note 3: The values ​​in the columns 'Present Value of the FIXED PECUNIARY CONSIDERATION (R$)' must be adjusted by the discount presented by the WINNING BIDDER in the context of the BIDDING, if applicable and according to the COMMERCIAL PROPOSAL in accordance with the model provided in EXHIBIT I.H.
Note 4: The values in the column 'Present Value of the FIXED PECUNIARY CONSIDERATION (R$)' will be converted into values of FIXED PECUNIARY CONSIDERATION in the form of EXHIBIT IX and subsequently must be adjusted in accordance with its terms.
Note 5: The values in the column 'Amount of the CONTRIBUTION (R$)' must be adjusted in accordance with item 8.3 of EXHIBIT IX.
Note 6: Each line of the table containing (i) a numbered sub-item and (ii) values in R$ in the columns 'Present Value of the FIXED PECUNIARY CONSIDERATION (R$)' and/or 'Amount of the CONTRIBUTION (R$)' constitutes an INVESTMENT PACKAGE. By way of example, the line containing sub-item 4.1.1.2 below constitutes an INVESTMENT PACKAGE, even though it is contained in the main item 'Ventures 4: Transpositions, Crossings, Permanent Way and Vehicles and Auxiliary Equipment' (line 26) and in the groups 'Transpositions and Crossings' (line 27) and 'OAES' (line 28), which are set out in the table for organizational purposes only. Therefore, the SUBSTANTIAL COMPLETION or FULL COMPLETION of the investments contemplated in this INVESTMENT PACKAGE would generate the right, in accordance with EXHIBIT IX, to the payment of FIXED PECUNIARY CONSIDERATION to be calculated using the Present Value of R$1,125,057.26 and a CONTRIBUTION installment of R$5,421,905.82.
# INVESTMENT PACKAGE | Investment Items | Contractual Month of Investment Completion | Present Value of FIXED PECUNIARY CONSIDERATION (R$) | Public CONTRIBUTION Amount (R$)
Ventures 4: Transpositions, Crossings, Permanent Track and Vehicles and Auxiliary Equipment
Transposições e Travessias
OAES
4.1.1.1 | OAES in the km 32+205 | 48 | 0 | 5640193.6759
4.1.1.2 | OAES in the km 34+720 | 72 | 1125057.2567 | 5421905.8165
4.1.1.3 | Railway bridge in the km 37+530 | 72 | 877633.906 | 4229516.6326
4.1.1.4 | Railway bridge in the km 50+770 | 72 | 877633.906 | 4229516.6326
4.1.1.5 | Railway bridge Cezar of Souza | 60 | 5882107.7892 | 10504321.9907
Note 7: Each INVESTMENT PACKAGE provided for in group 7 ('Projects') of the table set forth in the 'EXHIBIT IX' tab consists of the respective EXECUTIVE PROJECTS and BASIC PROJECTS of the VENTURES applicable to each of the LINES.
Note 8: The INVESTMENT PACKAGE '4.3.1. Vehicles and Auxiliary Equipment' will be considered completed upon the availability of all vehicles and equipment listed in item 4.3 of ANNEX II.F.
Note 9: The Contractual Month of Investment Completion stated in the cells of column D must be counted from the beginning of the PRE-OPERATIONAL PHASE.
ANEXO IX.A – CONTRAPRESTAÇÃO PECUNIÁRIA E APORTE

## Anexo IX.A
# Investment Package | Item | Contractual Month of Investment Completion | Present Value of the FIXED PECUNIARY CONSIDERATION (R$) | Nominal value of the PUBLIC CONTRIBUTION (R$)
1. | Venture 1: Stations - Construction Works, Overhead Line, Permanent Track and Systems |  | 490045759.9136 | 2091753501.0435
1.1.. | Stations - Initial Works |  | 0 | 80035368.9154
1.1.1. | Initial Works -Brás Station | 12 | 0 | 8839416.2832
1.1.2. | Initial Works - Guaianases Station | 12 | 0 | 1317814.594
1.1.3. | Initial Works - Braz Cubas Station | 12 | 0 | 1083968.1817
1.1.4. | Initial Works - Palmeiras-Barra Funda Station | 12 | 0 | 4796607.751
1.1.5. | Initial Works - Luz Station | 12 | 0 | 361083.5619
1.1.6. | Initial Works - Tatuapé Station | 12 | 0 | 4755242.8018
1.1.7. | Initial Works - Corinthians-Itaquera Station | 12 | 0 | 2206906.7867
1.1.8. | Initial Works - Dom Bosco Station | 12 | 0 | 6464125.138
1.1.9. | Initial Works - José Bonifácio Station | 12 | 0 | 5526295.4485
1.1.10. | Initial Works - Antônio Gianetti Neto Station | 12 | 0 | 3602616.4966
1.1.11. | Initial Works - Ferraz of Vasconcelos Station | 12 | 0 | 5431674.8576
1.1.12. | Initial Works - Poá Station | 12 | 0 | 1565858.7458
1.1.13. | Initial Works - Calmon Viana Station | 12 | 0 | 4346381.2574
1.1.14. | Initial Works - Suzano Station | 12 | 0 | 99920.5698
1.1.15. | Initial Works - USP Leste Station | 12 | 0 | 3831542.0801
1.1.16. | Initial Works - Comendador Ermelino Station | 12 | 0 | 2254768.3104
1.1.17. | Initial Works - São Miguel Paulista Station | 12 | 0 | 1781020.1022
1.1.18. | Initial Works - Jardim Helena - Vila Mara Station | 12 | 0 | 2097279.4061
1.1.19. | Initial Works - Itaim Paulista Station | 12 | 0 | 3517434.2489
1.1.20. | Initial Works - Jardim Romano Station | 12 | 0 | 3445037.7437
1.1.21. | Initial Works - Engenheiro Goulart Station | 12 | 0 | 5801138.2849
1.1.22. | Initial Works - Guarulhos-CECAP Station | 12 | 0 | 6453680.0311
1.1.23. | Initial Works - Airport-Guarulhos Station | 12 | 0 | 455556.234
1.2.. | Stations - Construction Works, Overhead Line, Permanent Track and Systems |  | 490045759.9136 | 2011718132.1281
1.2.1. | Station Bom Retiro | 84 | 0 | 283547913.9417
1.2.1.1 | Construction Work | 84 | 0 | 0
1.2.1.2 | Mobilization, earthmoving, retaining structures, and foundations | 48 | 0 | 22579202.6003
1.2.1.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 72 | 0 | 94833719.2167
1.2.1.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 84 | 0 | 33114068.9932
1.2.1.5 | Overhead line | 72 | 0 | 46103029.9996
1.2.1.6 | Permanent Track | 72 | 0 | 72098853.6534
1.2.1.7 | Telecom and Systems | 84 | 0 | 14819039.4785
1.2.2. | Station Lajeado | 84 | 37084704.975 | 95126262.9025
1.2.2.1 | Construction Work | 84 | 0 | 0
1.2.2.2 | Mobilization, earthworks, retaining structures, and foundations | 48 | 0 | 14377153.6468
1.2.2.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 72 | 9397471.4753 | 45288544.1598
1.2.2.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 84 | 11938494.2819 | 0
1.2.2.5 | Overhead line | 72 | 2869943.7179 | 13830908.9999
1.2.2.6 | Permanent Track | 72 | 4488200.7129 | 21629656.096
1.2.2.7 | Telecom and Systems | 84 | 8390594.787 | 0
1.2.3. | Station Brás | 60 | 15302651.8373 | 27327615.8771
1.2.3.1 | Construction Work - Station Brás | 60 | 10997727.6565 | 19639842.8267
1.2.3.2 | Overhead line - Station Brás | 60 | 0 | 0
1.2.3.3 | Telecom and Systems - Station Brás | 60 | 4304924.1809 | 7687773.0504
1.2.4. | Station Guaianases - First Phase | 60 | 19374312.6014 | 7687773.0504
1.2.4.1 | Construction Work - Station Guaianases | 60 | 15069388.4205 | 0
1.2.4.2 | Telecom and Systems - Station Guaianases | 60 | 4304924.1809 | 7687773.0504
1.2.5. | Station Braz Cubas | 60 | 7564907.0208 | 51039989.848
1.2.5.1 | Construction Work | 60 | 0 | 0
1.2.5.2 | Mobilization, earthworks, retaining structures, and foundations | 36 | 0 | 7219114.6681
1.2.5.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 48 | 0 | 30311394.901
1.2.5.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 60 | 3259982.8399 | 5821707.2285
1.2.5.5 | Telecom and Systems | 60 | 4304924.1809 | 7687773.0504
1.2.6. | Station Jundiapeba | 84 | 22469510.5332 | 92514682.5744
1.2.6.1 | Construction Work | 84 | 0 | 0
1.2.6.2 | Mobilization, earthworks, retaining structures, and foundations | 36 | 0 | 10077082.6189
1.2.6.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 48 | 0 | 42311342.1459
1.2.6.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 60 | 4550574.125 | 8126456.9717
1.2.6.5 | Overhead line | 60 | 5309959.4924 | 9482574.3195
1.2.6.6 | Permanent Track | 60 | 8304052.7348 | 14829453.4681
1.2.6.7 | Telecom and Systems | 60 | 4304924.1809 | 7687773.0504
1.2.7. | Station Mogi das Cruzes | 84 | 15843750.0266 | 100003655.9513
1.2.7.1 | Construction Work | 84 | 0 | 0
1.2.7.2 | Mobilization, earthworks, retaining structures, and foundations | 36 | 0 | 13793600.3545
1.2.7.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 48 | 0 | 57916141.615
1.2.7.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 60 | 6228866.3533 | 11123566.612
1.2.7.5 | Overhead line | 60 | 5309959.4924 | 9482574.3195
1.2.7.6 | Telecom and Systems | 60 | 4304924.1809 | 7687773.0504
1.2.8. | Station Estudantes | 60 | 22824812.116 | 112912701.868
1.2.8.1 | Construction Work | 60 | 0 | 0
1.2.8.2 | Mobilization, earthworks, retaining structures, and foundations | 36 | 0 | 13878659.1955
1.2.8.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 48 | 0 | 58273284.0403
1.2.8.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 60 | 6267276.9306 | 11192160.573
1.2.8.5 | Overhead line | 60 | 4778963.5432 | 8534316.8875
1.2.8.6 | Permanent Track | 60 | 7473647.4613 | 13346508.1213
1.2.8.7 | Telecom and Systems | 60 | 4304924.1809 | 7687773.0504
1.2.9. | Station Palmeiras-Barra Funda | 36 | 0 | 35218825.3326
1.2.9.1 | Construction Work - Station Palmeiras-Barra Funda | 36 | 0 | 2021898.9495
1.2.9.2 | Telecom and Systems - Station Palmeiras-Barra Funda | 36 | 0 | 13302265.3839
1.2.9.3 | Station Luz | 12 | 0 | 0
1.2.9.4 | Construction Work - Station Luz | 36 | 0 | 6592395.6153
1.2.9.5 | Telecom and Systems - Station Luz | 36 | 0 | 13302265.3839
1.2.10. | Station Tatuapé | 36 | 0 | 19883339.9606
1.2.10.1 | Construction Work - Station Tatuapé | 36 | 0 | 6581074.5767
1.2.10.2 | Telecom and Systems - Station Tatuapé | 36 | 0 | 13302265.3839
1.2.11. | Station Corinthians-Itaquera | 36 | 0 | 15802504.6887
1.2.11.1 | Construction Work - Station Corinthians-Itaquera | 36 | 0 | 2500239.3049
1.2.11.2 | Telecom and Systems - Station Corinthians-Itaquera | 36 | 0 | 13302265.3839
1.2.12. | Station Dom Bosco | 36 | 0 | 21626558.9528
1.2.12.1 | Construction Work - Station Dom Bosco | 36 | 0 | 8324293.5689
1.2.12.2 | Telecom and Systems - Station Dom Bosco | 36 | 0 | 13302265.3839
1.2.13. | Station José Bonifácio | 36 | 0 | 16350443.5504
1.2.13.1 | Construction Work - Station José Bonifácio | 36 | 0 | 3048178.1666
1.2.13.2 | Telecom and Systems - Station José Bonifácio | 36 | 0 | 13302265.3839
1.2.14. | Station Antônio Gianetti Neto | 48 | 0 | 31123238.9286
1.2.14.1 | Construction Work - Station Antônio Gianetti Neto | 48 | 0 | 17508461.6172
1.2.14.2 | Telecom and Systems - Station Antônio Gianetti Neto | 48 | 0 | 13614777.3114
1.2.15. | Station Ferraz of Vasconcelos | 36 | 0 | 14744164.9082
1.2.15.1 | Construction Work - Station Ferraz of Vasconcelos | 36 | 0 | 1441899.5243
1.2.15.2 | Telecom and Systems - Station Ferraz of Vasconcelos | 36 | 0 | 13302265.3839
1.2.16. | Station Poá | 36 | 0 | 14865368.3046
1.2.16.1 | Construction Work - Station Poá | 36 | 0 | 1563102.9207
1.2.16.2 | Telecom and Systems - Station Poá | 36 | 0 | 13302265.3839
1.2.17. | Station Calmon Viana | 48 | 0 | 32841481.7336
1.2.17.1 | Construction Work - Station Calmon Viana | 48 | 0 | 19226704.4222
1.2.17.2 | Telecom and Systems - Station Calmon Viana | 48 | 0 | 13614777.3114
1.2.18. | Station Suzano | 36 | 0 | 17009902.5042
1.2.18.1 | Construction Work - Station Suzano | 36 | 0 | 3707637.1204
1.2.18.2 | Telecom and Systems - Station Suzano | 36 | 0 | 13302265.3839
1.2.19. | Station Penha | 48 | 0 | 13302265.3839
1.2.19.1 | Initial Works | 36 | 0 | 0
1.2.19.2 | Construction Work | 48 | 0 | 0
1.2.19.3 | Telecom and Systems | 48 | 0 | 13302265.3839
1.2.20. | Station Cezar of Souza | 60 | 8746734.4747 | 76383705.1397
1.2.20.1 | Construction Work | 60 | 0 | 0
1.2.20.2 | Mobilization, earthworks, retaining structures, and foundations | 12 | 0 | 11685328.1854
1.2.20.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 36 | 0 | 49078378.3786
1.2.20.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 36 | 5278367.1569 | 9426156.4372
1.2.20.5 | Overhead line | 48 | 3468367.3177 | 6193842.1384
1.2.21. | Station Itaquaquecetuba | 60 | 13240109.2975 | 150299974.3819
1.2.21.1 | Construction Work | 48 | 0 | 0
1.2.21.2 | Mobilization, earthworks, retaining structures, and foundations | 48 | 0 | 15859896.8357
1.2.21.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 60 | 0 | 66592043.2326
1.2.21.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 12 | 7161957.3736 | 12789889.1064
1.2.21.5 | Overhead line | 60 | 0 | 17241059.3965
1.2.21.6 | Permanent Track | 60 | 0 | 26962666.4077
1.2.21.7 | Telecom and Systems | 12 | 6078151.9239 | 10854419.403
1.2.22. | Station USP Leste | 60 | 6906680.7619 | 12334013.794
1.2.22.1 | Construction Work - Station USP Leste | 60 | 828528.8379 | 1479594.391
1.2.22.2 | Telecom and Systems - Station USP Leste | 12 | 6078151.9239 | 10854419.403
1.2.23. | Station Comendador Ermelino | 60 | 6498769.7555 | 11605562.581
1.2.23.1 | Construction Work - Station Comendador Ermelino | 60 | 420617.8316 | 751143.178
1.2.23.2 | Telecom and Systems - Station Comendador Ermelino | 12 | 6078151.9239 | 10854419.403
1.2.24. | Station São Miguel Paulista | 72 | 6781854.5173 | 12111097.9427
1.2.24.1 | Construction Work - Station São Miguel Paulista | 72 | 703702.5934 | 1256678.5397
1.2.24.2 | Telecom and Systems - Station São Miguel Paulista | 12 | 6078151.9239 | 10854419.403
1.2.25. | Station Jardim Helena - Vila Mara | 72 | 3300588.0294 | 15906281.5051
1.2.25.1 | Construction Work - Station Jardim Helena - Vila Mara | 72 | 229236.7148 | 1104743.6654
1.2.25.2 | Telecom and Systems - Station Jardim Helena - Vila Mara | 12 | 3071351.3145 | 14801537.8397
1.2.26. | Station Itaim Paulista | 72 | 3501215.7249 | 16873151.8248
1.2.26.1 | Construction Work - Station Itaim Paulista | 72 | 429864.4104 | 2071613.9851
1.2.26.2 | Telecom and Systems - Station Itaim Paulista | 12 | 3071351.3145 | 14801537.8397
1.2.27. | Station Jardim Romano | 48 | 3371049.1845 | 16245849.7755
1.2.27.1 | Construction Work - Station Jardim Romano | 48 | 299697.87 | 1444311.9359
1.2.27.2 | Telecom and Systems - Station Jardim Romano | 12 | 3071351.3145 | 14801537.8397
1.2.28. | Station Aracaré | 84 | 7862909.242 | 102777288.6017
1.2.28.1 | Construction Work | 24 | 0 | 61834027.3467
1.2.28.2 | Telecom and Systems | 12 | 0 | 20772083.062
1.2.28.3 | Station Manoel Feio | 84 | 0 | 0
1.2.28.4 | Construction Work | 60 | 0 | 0
1.2.28.5 | Telecom and Systems | 12 | 7862909.242 | 20171178.1931
1.2.29. | Station Engenheiro Goulart | 60 | 3613350.6735 | 4192304.9267
1.2.29.1 | Construction Work - Station Engenheiro Goulart | 60 | 1265784.6443 | 0
1.2.29.2 | Telecom and Systems - Station Engenheiro Goulart | 12 | 2347566.0291 | 4192304.9267
1.2.30. | Station Guarulhos-CECAP | 60 | 3313591.2759 | 4192304.9267
1.2.30.1 | Construction Work - Station Guarulhos-CECAP | 60 | 966025.2468 | 0
1.2.30.2 | Telecom and Systems - Station Guarulhos-CECAP | 12 | 2347566.0291 | 4192304.9267
1.2.31. | Station Airport-Guarulhos | 72 | 3921605.7356 | 4192304.9267
1.2.31.1 | Construction Work - Station Airport-Guarulhos | 60 | 1574039.7065 | 0
1.2.31.2 | Telecom and Systems - Station Airport-Guarulhos | 72 | 2347566.0291 | 4192304.9267
1.2.32. | Station Jardim dos Eucaliptos | 84 | 51925536.9385 | 98820202.658
1.2.32.1 | Construction Work | 84 | 0 | 0
1.2.32.2 | Mobilization, earthworks, retaining structures, and foundations | 12 | 8225592.0708 | 14689337.6954
1.2.32.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 84 | 17457337.575 | 84130864.9626
1.2.32.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 60 | 22177702.3069 | 0
1.2.32.5 | Telecom and Systems | 72 | 4064904.9858 | 0
1.2.33. | Station São João | 84 | 44141586.7757 | 82748297.6041
1.2.33.1 | Construction Work | 84 | 0 | 0
1.2.33.2 | Mobilization, earthworks, retaining structures, and foundations | 12 | 6887799.4817 | 12300295.4308
1.2.33.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 84 | 14618113.768 | 70448002.1733
1.2.33.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 60 | 18570768.5402 | 0
1.2.33.5 | Telecom and Systems | 72 | 4064904.9858 | 0
1.2.34. | Station Presidente Dutra | 84 | 57994527.0614 | 111351145.3013
1.2.34.1 | Construction Work | 84 | 0 | 0
1.2.34.2 | Mobilization, earthworks, retaining structures, and foundations | 12 | 9268642.1727 | 16552026.1253
1.2.34.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 84 | 19671023.5418 | 94799119.1761
1.2.34.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 60 | 24989956.3611 | 0
1.2.34.5 | Telecom and Systems | 72 | 4064904.9858 | 0
1.2.35. | Station Bonsucesso | 84 | 60151319.7463 | 115804381.3226
1.2.35.1 | Construction Work | 84 | 0 | 0
1.2.35.2 | Mobilization, earthworks, retaining structures, and foundations | 12 | 9639320.4543 | 17213986.7972
1.2.35.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 84 | 20457721.4278 | 98590394.5254
1.2.35.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 48 | 25989372.8784 | 0
1.2.35.5 | Telecom and Systems | 72 | 4064904.9858 | 0
1.2.36. | Station Cangaíba | 72 | 59458705.8053 | 168674825.1295
1.2.36.1 | Construction Work | 72 | 0 | 0
1.2.36.2 | Mobilization, earthworks, retaining structures, and foundations | 12 | 0 | 39266657.9175
1.2.36.3 | Structures, enclosures, concealed installations (electrical, plumbing, air conditioning, systems), waterproofing, and roofing | 60 | 25666227.598 | 123691365.8149
1.2.36.4 | Finishes, visible installations (electrical, plumbing, air conditioning, systems), and visual communication | 12 | 32606229.4758 | 0
1.2.36.5 | Telecom and Systems | 48 | 1186248.7315 | 5716801.3972
1.2.37. | Station Gabriela Mistral | 72 | 2394852.4914 | 4276749.5243
1.2.37.1 | Telecom and Systems - Station Gabriela Mistral | 72 | 2394852.4914 | 4276749.5243
1.2.38. | Station Guaianases - Second Phase | 108 | 2456123.3119 | 0
1.2.37.1 | Construction Work | 108 | 2456123.3119 | 0
2. | Venture 2: Systems |  | 964565269.5959 | 2685084938.4871
2.1.. | Signage |  | 603036334.313 | 1647662180.1545
2.1.1. | Segment Barra Funda - km 4+452 (line 7) / Luz - km 0+000 (extension 4.452 m) | 96 | 15450324.6271 | 53949782.1711
2.1.1.1 | Manufacturing and delivery of materials in the field | 24 | 13620805.6309 | 34942244.5379
2.1.1.2 | Installation completion / commissioning | 36 | 0 | 17768887.322
2.1.1.3 | Final acceptance | 96 | 1829518.9963 | 0
2.1.1.4 | CFTV | 36 | 0 | 1238650.3112
2.1.2. | Segment Luz - km 0+000 / Brás km 2+240 (extension of 2.240 m double-track) | 96 | 4271606.9275 | 29921900.2213
2.1.2.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 25025560.8602
2.1.2.2 | Installation completion / commissioning | 60 | 3058514.4641 | 4468846.2191
2.1.2.3 | Final acceptance | 96 | 920512.7025 | 0
2.1.2.4 | CFTV | 60 | 292579.7608 | 427493.142
2.1.3. | Segment Engenheiro Gualberto - km 8+500 / Corinthians Itaquera - km 19+450 (extension 10.950 m double-track) | 96 | 20516005.6523 | 146652446.3554
2.1.3.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 122334772.9548
2.1.3.2 | Installation completion / commissioning | 60 | 14951220.2598 | 21845475.9373
2.1.3.3 | Final acceptance | 96 | 4499827.7199 | 0
2.1.3.4 | Track Enclosure | 12 | 0 | 916170.1419
2.1.3.5 | CFTV | 60 | 1064957.6726 | 1556027.3213
2.1.4. | Segment Tunel 3 km 23+040 / Guaianazes km 24+800 -(Extension of 1760m double-track) | 96 | 3322411.0099 | 23460603.3604
2.1.4.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 19662940.6758
2.1.4.2 | Installation completion / commissioning | 60 | 2403118.5075 | 3511236.315
2.1.4.3 | Final acceptance | 96 | 723259.9806 | 0
2.1.4.4 | CFTV | 60 | 196032.5219 | 286426.3695
2.1.5. | Segment Guaianazes km 24+800 / Suzano km 36+940 (Extension of 12.140m double-track. Rail TR 68 from km 25+000 to km 33+800 - Extension of 8.800m) | 96 | 57761567.2698 | 57207522.616
2.1.5.1 | Manufacturing and delivery of materials in the field | 72 | 32730896.5012 | 52579201.9509
2.1.5.2 | Installation completion / commissioning | 84 | 19879509.3775 | 0
2.1.5.3 | Final acceptance | 96 | 3616299.9028 | 0
2.1.5.4 | Track Enclosure | 12 | 0 | 4628320.6651
2.1.5.5 | CFTV | 84 | 1534861.4883 | 0
2.1.6. | Segment Suzano km 36+940 / Estudantes km 50+770 (Extension of 13.830m double-track) | 96 | 90750068.4998 | 84128299.3928
2.1.6.1 | Manufacturing and delivery of materials in the field | 72 | 51439579.3877 | 82632995.7933
2.1.6.2 | Installation completion / commissioning | 84 | 31242456.2149 | 0
2.1.6.3 | Final acceptance | 96 | 5683344.0517 | 0
2.1.6.4 | Track Enclosure | 12 | 0 | 1495303.5995
2.1.6.5 | CFTV | 84 | 2384688.8455 | 0
2.1.7. | Segment Brás - km 2+240/ SE Engenheiro Gualberto - km 8+500 (extension of 6.260 m with 4 tracks) - L11 | 96 | 79355033.6115 | 69938292.754
2.1.7.1 | Manufacturing and delivery of materials in the field | 72 | 43537043.8627 | 69938292.754
2.1.7.2 | Installation completion / commissioning | 84 | 28283120.1598 | 0
2.1.7.3 | Final acceptance | 96 | 5145008.498 | 0
2.1.7.4 | CFTV | 84 | 2389861.0909 | 0
2.1.8. | Construction of New Line Estudantes - Cezar of Souza - 4,26 km | 96 | 13014322.4713 | 71873889.9503
2.1.8.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 55860626.92
2.1.8.2 | Installation completion / commissioning | 60 | 6827041.2145 | 9975103.1677
2.1.8.3 | Final acceptance | 96 | 2054715.8538 | 0
2.1.8.4 | Track Enclosure | 60 | 3641122.2429 | 5320104.1092
2.1.8.5 | CFTV | 60 | 491443.16 | 718055.7533
2.1.9. | Segment SE Engenheiro Gualberto km 8+500 / USP Leste km 17+200 (Extension of 8.700 m double-track) | 96 | 16455962.7012 | 116113157.8464
2.1.9.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 97197490.8408
2.1.9.2 | Installation completion / commissioning | 60 | 11879051.7133 | 17356679.5119
2.1.9.3 | Final acceptance | 96 | 3575205.5857 | 0
2.1.9.4 | Track Enclosure | 24 | 86375.2267 | 221583.3905
2.1.9.5 | CFTV | 60 | 915330.1756 | 1337404.1033
2.1.10. | Segment USP Leste km 17+200 / Engenheiro Manoel Feio km 33+150 (Extension of 15.950m double-track) | 96 | 100899222.2086 | 89515801.775
2.1.10.1 | Manufacturing and delivery of materials in the field | 72 | 55464524.7292 | 89098703.6283
2.1.10.2 | Installation completion / commissioning | 84 | 36031610.7467 | 0
2.1.10.3 | Final acceptance | 96 | 6554543.5738 | 0
2.1.10.4 | Track Enclosure | 24 | 162588.662 | 417098.1468
2.1.10.5 | CFTV | 84 | 2685954.4969 | 0
2.1.11. | Segment Engenheiro Manoel Feio km 33+150 / Calmon Viana km 40+140 ( Extension of 7.990 m double-track) | 96 | 14981475.4526 | 106357481.4091
2.1.11.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 89265281.8182
2.1.11.2 | Installation completion / commissioning | 60 | 10909611.8608 | 15940214.862
2.1.11.3 | Final acceptance | 96 | 3283435.9344 | 0
2.1.11.4 | CFTV | 60 | 788427.6573 | 1151984.7288
2.1.12. | Construction of New Line Calmon Viana - Suzano - 3,95 km | 96 | 21904058.8172 | 38085501.5635
2.1.12.1 | Manufacturing and delivery of materials in the field | 60 | 15292572.3205 | 22344231.0957
2.1.12.2 | Installation completion / commissioning | 72 | 4967713.8136 | 7980179.4562
2.1.12.3 | Final acceptance | 96 | 1643772.6831 | 0
2.1.12.4 | Track Enclosure | 36 | 0 | 6665392.0935
2.1.12.5 | CFTV | 48 | 0 | 1095698.9181
2.1.13. | Segment Eng Goulart - Airport-Guarulhos | 96 | 54760147.0431 | 75811026.3797
2.1.13.1 | Manufacturing and delivery of materials in the field | 60 | 38231430.8013 | 55860577.7393
2.1.13.2 | Installation completion / commissioning | 72 | 12419284.5341 | 19950448.6405
2.1.13.3 | Final acceptance | 96 | 4109431.7077 | 0
2.1.14. | Construction of New Line Guarulhos Airport - Bonsucesso - 11 km | 96 | 99772811.4347 | 1997460.9191
2.1.14.1 | Manufacturing and delivery of materials in the field | 84 | 69578282.8212 | 0
2.1.14.2 | Installation completion / commissioning | 96 | 22601874.3923 | 0
2.1.14.3 | Final acceptance | 96 | 4520374.8785 | 0
2.1.14.4 | Track Enclosure | 60 | 1367078.3941 | 1997460.9191
2.1.14.5 | CFTV | 96 | 1705200.9486 | 0
2.1.15. | Construction of New Line Engenheiro Goulart - Gabriela Mistral - 5,5 km | 96 | 2054715.8538 | 77530365.9122
2.1.15.1 | Manufacturing and delivery of materials in the field | 36 | 0 | 55877004.1573
2.1.15.2 | Installation completion / commissioning | 48 | 0 | 19950223.9
2.1.15.3 | Final acceptance | 96 | 2054715.8538 | 0
2.1.15.4 | CFTV | 48 | 0 | 1703137.855
2.1.16. | On-board Train Equipment (including demobilization) | 36 | 0 | 475744980.5739
2.1.17. | On-board equipment - MRS (including demobilization) | 36 | 0 | 13464480.5823
2.1.18. | On-board equipment for Auxiliary vehicles | 36 | 0 | 31417121.3587
2.1.19. | Spare Track equipment | 36 | 7766600.7324 | 84492065.0134
2.2.. | Energy |  | 316630227.4514 | 854725041.6878
2.2.1. | Energy - Tracks |  | 201416038.928 | 449715026.9496
2.2.1.1 | Segment Luz - km 0+000 / Brás km 2+240 (extension of 2.240 m double-track) | 60 | 1748035.6407 | 14473152.4327
2.2.1.2 | Manufacturing and delivery of materials in the field | 48 | 0 | 11919068.5611
2.2.1.3 | Installation completion / commissioning | 60 | 1456696.3672 | 2128403.2263
2.2.1.4 | Final acceptance | 60 | 291339.2734 | 425680.6453
2.2.2. | Segment Engenheiro Gualberto - km 8+500 / Corinthians Itaquera - km 19+450 (extension 10.950 m double-track) | 60 | 8545084.9399 | 70750454.9725
2.2.2.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 58265089.6181
2.2.2.2 | Installation completion / commissioning | 60 | 7120904.1166 | 10404471.1286
2.2.2.3 | Final acceptance | 60 | 1424180.8233 | 2080894.2257
2.2.3. | Segment Guaianazes km 24+800 / Suzano km 36+940 (Extension of 12.140m double-track. Rail TR 68 from km 25+000 to km 33+800 - Extension of 8.800m) | 96 | 13389709.1242 | 12521100.2551
2.2.3.1 | Manufacturing and delivery of materials in the field | 72 | 7794466.6584 | 12521100.2551
2.2.3.2 | Installation completion / commissioning | 84 | 4734064.4343 | 0
2.2.3.3 | Final acceptance | 96 | 861178.0315 | 0
2.2.4. | Segment Suzano km 36+940 / Estudantes km 50+770 (Extension of 13.830m double-track) | 96 | 42086290.27 | 39356094.6656
2.2.4.1 | Manufacturing and delivery of materials in the field | 72 | 24499425.8832 | 39356094.6656
2.2.4.2 | Installation completion / commissioning | 84 | 14880025.2559 | 0
2.2.4.3 | Final acceptance | 96 | 2706839.1309 | 0
2.2.5. | Segment Brás - km 2+240/ SE Engenheiro Gualberto - km 8+500 (extension of 6.260 m with 4 tracks) - L11 | 96 | 36656647.7058 | 33309915.0521
2.2.5.1 | Manufacturing and delivery of materials in the field | 72 | 20735639.5986 | 33309915.0521
2.2.5.2 | Installation completion / commissioning | 84 | 13470565.163 | 0
2.2.5.3 | Final acceptance | 96 | 2450442.9442 | 0
2.2.6. | Segment Estudante - Cezar of Souza | 60 | 12350948.9812 | 102261740.6271
2.2.6.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 84215564.1891
2.2.6.2 | Installation completion / commissioning | 60 | 10292457.4843 | 15038480.365
2.2.6.3 | Final acceptance | 60 | 2058491.4969 | 3007696.073
2.2.7. | Sebastião Gualberto - USP Leste | 60 | 6789245.5687 | 56212690.2521
2.2.7.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 46292810.9294
2.2.7.2 | Installation completion / commissioning | 60 | 5657704.6406 | 8266566.1022
2.2.7.3 | Final acceptance | 60 | 1131540.9281 | 1653313.2204
2.2.8. | USP Leste - Eng Manoel Feio | 96 | 46699163.8106 | 42435554.719
2.2.8.1 | Manufacturing and delivery of materials in the field | 72 | 26416409.872 | 42435554.719
2.2.8.2 | Installation completion / commissioning | 84 | 17160983.5743 | 0
2.2.8.3 | Final acceptance | 96 | 3121770.3643 | 0
2.2.9. | USP Leste - Eng Manoel Feio - Calmon Viana | 60 | 6235180.7005 | 51625217.8292
2.2.9.1 | Manufacturing and delivery of materials in the field | 48 | 0 | 42514891.8766
2.2.9.2 | Installation completion / commissioning | 60 | 5195983.917 | 7591938.2939
2.2.9.3 | Final acceptance | 60 | 1039196.7834 | 1518387.6588
2.2.10. | Segment Calmon Viana - Suzano - 3,95 km | 84 | 6580313.2825 | 9042437.6391
2.2.10.1 | Manufacturing and delivery of materials in the field | 60 | 4560092.9757 | 6662827.4911
2.2.10.2 | Installation completion / commissioning | 72 | 1481322.8535 | 2379610.148
2.2.10.3 | Final acceptance | 84 | 538897.4534 | 0
2.2.11. | Segment Guarulhos Airport - Bonsucesso - 11 km | 96 | 20024400.6578 | 0
2.2.11.1 | Manufacturing and delivery of materials in the field | 84 | 14408022.1913 | 0
2.2.11.2 | Installation completion / commissioning | 96 | 4680315.3887 | 0
2.2.11.3 | Final acceptance | 96 | 936063.0777 | 0
2.2.12. | Segment Engenheiro Goulart - Gabriela Mistral - 5,5 km | 60 | 311018.2461 | 17726668.5051
2.2.12.1 | Manufacturing and delivery of materials in the field | 36 | 0 | 12727891.3989
2.2.12.2 | Installation completion / commissioning | 48 | 0 | 4544343.1875
2.2.12.3 | Final acceptance | 60 | 311018.2461 | 454433.9187
2.2.1. | Energy - Substation of Energy |  | 115214188.5233 | 405010014.7383
2.2.1.1 | SE Sebastião Gualberto | 36 | 5959514.9054 | 64832960.8006
2.2.1.2 | SE Dom Bosco | 72 | 1917534.2199 | 17455282.3797
2.2.1.3 | SE Guaianases | 72 | 0 | 20535626.329
2.2.1.4 | SE Ermelino Matarazzo | 36 | 2344548.2762 | 70246102.157
2.2.1.5 | SE Calmon Viana | 36 | 5959514.9054 | 64832960.8006
2.2.1.6 | SE São Miguel Paulista | 24 | 46415048.932 | 76545786.4649
2.2.1.7 | SE São João (Primária/ Retificadora 4MW) | 72 | 20766800.6019 | 40773299.5558
2.2.1.8 | SE Presidente Dutra (4MW) | 60 | 15228987.1081 | 22251325.687
2.2.1.9 | SE Braz Cubas | 72 | 7917488.59 | 12718723.7752
2.2.1.10 | SE Engenheiro Manoel Feio | 60 | 8704750.9844 | 12718656.0605
2.2.1.11 | Spare parts | 12 | 0 | 2099290.7279
2.3.1. | CCO |  | 44898707.8315 | 182697716.6448
2.3.2. | CCO Line 11 | 84 | 19989929.6668 | 67404998.1625
2.3.2.1 | Manufacturing and delivery of materials in the field | 24 | 17417770.1393 | 44682818.3302
2.3.2.2 | Installation completion / commissioning | 36 | 0 | 22722179.8324
2.3.2.3 | Final acceptance | 84 | 2572159.5274 | 0
2.3.3. | CCO Line 12 | 84 | 9067996.0232 | 61878428.9404
2.3.3.1 | Manufacturing and delivery of materials in the field | 24 | 7000427.5312 | 43613751.89
2.3.3.2 | Installation completion / commissioning | 36 | 0 | 18264677.0504
2.3.3.3 | Final acceptance | 84 | 2067568.492 | 0
2.3.4. | CCO Line 13 | 84 | 15840782.1415 | 53414289.5418
2.3.4.1 | Manufacturing and delivery of materials in the field | 24 | 13802504.8996 | 35408368.2352
2.3.4.2 | Installation completion / commissioning | 36 | 0 | 18005921.3066
2.3.4.3 | Final acceptance | 84 | 2038277.2419 | 0
3. | Venture 3: Yards and Maintenance Complexes |  | 273465140.0206 | 749706215.2276
3.1.. | Luz Complex | 84 | 68043172.0204 | 180261556.7814
3.1.1. | Construction Work | 84 | 49109624.6866 | 130102362.0168
3.1.2. | Overhead line | 84 | 6944452.3433 | 18397404.9597
3.1.3. | Permanent Track | 84 | 11713494.1866 | 31031661.7338
3.1.4. | CFTV | 84 | 275600.8038 | 730128.0711
3.2.. | Braz Cubas Lavatory | 24 | 56436115.0206 | 93072115.8046
3.2.1. | Construction Work | 24 | 42843356.4439 | 70655498.3622
3.2.2. | Overhead line | 24 | 4850239.4293 | 7998815.0439
3.2.3. | Permanent Track | 24 | 8181098.8902 | 13491931.2401
3.2.4. | CFTV | 24 | 561420.2571 | 925871.1584
3.3.. | Engenheiro São Paulo Shelter | 60 | 83581355.4343 | 122501537.8482
3.3.1. | Construction Work | 60 | 55338347.5507 | 80855777.577
3.3.2. | Overhead line | 60 | 10318684.0156 | 15076800.385
3.3.3. | Permanent Track | 60 | 17404949.9161 | 25430661.0415
3.3.4. | CFTV | 60 | 519373.9518 | 1138298.8448
3.4.. | Calmon Viana Base | 36 | 0 | 112930696.9019
3.4.1. | Construction Work | 36 | 0 | 97642082.6759
3.4.2. | Overhead line | 36 | 0 | 0
3.4.3. | Permanent Track | 36 | 0 | 12384391.7222
3.4.4. | CFTV | 36 | 0 | 2904222.5038
3.5.. | TLS Shipyard - Jundiapeba | 36 | 0 | 40769000.6069
3.5.1. | Construction Work | 36 | 0 | 25436716.5651
3.5.2. | Overhead line | 36 | 0 | 0
3.5.3. | Permanent Track | 36 | 0 | 14110771.571
3.5.4. | CFTV | 36 | 0 | 1221512.4708
3.6.. | Mogi das Cruzes Base | 36 | 0 | 0
3.6.1. | Construction Work | 24 | 0 | 0
3.6.2. | CFTV | 24 | 0 | 0
3.7.. | Artur Alvim Base | 36 | 0 | 21939774.7001
3.7.1. | Construction Work | 36 | 0 | 17895244.0096
3.7.2. | Overhead line | 36 | 0 | 0
3.7.3. | Permanent Track | 36 | 0 | 3123904.0988
3.7.4. | CFTV | 36 | 0 | 920626.5917
3.8.. | Guaianases yard | 48 | 252039.173 | 15893666.5152
3.8.1. | Construction Work | 24 | 0 | 15247095.7723
3.8.2. | Overhead line | 48 | 0 | 0
3.8.3. | Permanent Track | 48 | 0 | 0
3.8.4. | CFTV | 24 | 252039.173 | 646570.7429
3.9.. | Test Track | 36 | 0 | 9430324.9747
3.9.1. | Construction Work | 36 | 0 | 0
3.9.2. | Overhead line | 36 | 0 | 3509949.086
3.9.3. | Permanent Track | 36 | 0 | 5920375.8888
3.9.4. | CFTV | 36 | 0 | 0
3.10.. | Cezar of Souza yard | 60 | 32009794.4981 | 46770041.7301
3.10.1. | Construction Work | 60 | 5818722.1464 | 8501831.451
3.10.2. | Overhead line | 60 | 4166695.7139 | 6088028.2261
3.10.3. | Permanent Track | 60 | 21709427.1128 | 31720004.0776
3.10.4. | CFTV | 60 | 314949.525 | 460177.9754
3.11.. | Roosevelt Complex | 84 | 0 | 0
3.11.1. | Construction Work | 84 | 0 | 0
3.11.2. | Overhead line | 84 | 0 | 0
3.11.3. | Permanent Track | 84 | 0 | 0
3.11.4. | CFTV | 84 | 0 | 0
3.12.. | Itaim Paulista yard | 84 | 7509041.8852 | 13262085.8196
3.12.1. | Construction Work | 84 | 3487914.861 | 6160176.8808
3.12.2. | Overhead line | 84 | 1385602.8077 | 2447180.8293
3.12.3. | Permanent Track | 84 | 2337153.404 | 4127760.8371
3.12.4. | CFTV | 84 | 298370.8124 | 526967.2724
3.13.. | Comendador Ermelino yard | 36 | 0 | 39176590.7568
3.13.1. | Construction Work | 36 | 0 | 35155172.4134
3.13.2. | Overhead line | 36 | 0 | 0
3.13.3. | Permanent Track | 36 | 0 | 3081812.7212
3.13.4. | CFTV | 36 | 0 | 939605.6222
3.14.. | Engenheiro Manoel Feio yard | 36 | 0 | 53144619.2941
3.14.1. | Construction Work | 36 | 0 | 14433917.4434
3.14.2. | Overhead line | 36 | 0 | 14065394.4026
3.14.3. | Permanent Track | 36 | 0 | 23724680.8564
3.14.4. | CFTV | 36 | 0 | 920626.5917
3.15.. | Eng Goulart parking yard | 24 | 336052.2307 | 554203.4939
3.15.1. | Construction Work | 24 | 0 | 0
3.15.2. | Overhead line | 24 | 0 | 0
3.15.3. | Permanent Track | 24 | 0 | 0
3.15.4. | CFTV | 24 | 336052.2307 | 554203.4939
3.16.. | Bonsucesso parking yard | 96 | 25297569.7583 | 0
3.16.1. | Construction Work | 96 | 25297569.7583 | 0
4. | Venture 4: Transpositions, Crossings, Permanent Track and Vehicles and Auxiliary Equipment |  | 1194662221.9816 | 1630806891.4904
4.1.. | Transpositions and Crossings |  | 494803659.1288 | 623414129.5775
4.1.1. | Line 14 |  | 369616348.9844 | 401186720.9886
4.1.1.1 | OAES in the km 32+205 | 48 | 0 | 5640193.6759
4.1.1.2 | OAES in the km 34+720 | 72 | 1125057.2567 | 5421905.8165
4.1.1.3 | Railway bridge in the km 37+530 | 72 | 877633.906 | 4229516.6326
4.1.1.4 | Railway bridge in the km 50+770 | 72 | 877633.906 | 4229516.6326
4.1.1.5 | Railway bridge Cezar of Souza | 60 | 5882107.7892 | 10504321.9907
4.1.1.6 | OAE in the km 31+850 | 60 | 5054385.1821 | 9026167.3742
4.1.1.7 | Construção of Express track Line 13 | 60 | 355799530.9444 | 346576397.8544
4.1.1.8 | Railway bridge - 5 m - Line 13 expansion 2 | 48 | 0 | 15558701.0119
4.1.2. | Passarelas |  | 19428155.6673 | 172020221.4228
4.1.2.1 | Segment between station Palmeiras - Barra Funda and station Guaianases | 36 | 0 | 28424160.8977
4.1.2.2 | Segment between station Guaianases and station Antônio Gianett Neto | 36 | 0 | 17830106.4718
4.1.2.3 | Segment between station Antônio Gianetti Neto and station Calmon Viana | 48 | 0 | 33403530.5103
4.1.2.4 | Segment between station Calmon Viana and station Estudantes | 60 | 19428155.6673 | 0
4.1.2.5 | Segment between station Brás and station USP Leste | 48 | 0 | 21314456.5024
4.1.2.6 | Segment between station USP Leste and station Itaim Paulista | 48 | 0 | 24866755.2691
4.1.2.7 | Segment between station Itaim Paulista and station Engenheiro Manoel Feio | 48 | 0 | 21314456.5024
4.1.2.8 | Segment between station Engenheiro Manoel Feio and station Calmon Viana | 48 | 0 | 24866755.2691
4.1.3. | Overpasses |  | 56509846.0469 | 11220151.5288
4.1.3.1 | Access ramp in the viaduto Argeu Batalha | 84 | 7058373.3396 | 0
4.1.3.2 | Overpass between station Braz Cubas and station Mogi das Cruzes | 60 | 25043817.1909 | 0
4.1.3.3 | Overpasses between station Estudantes and Cezar of Souza (extension da Line 11-Coral) (rodoviário) | 60 | 17423037.9339 | 0
4.1.3.4 | Overpass Campos Salles | 72 | 6984617.5824 | 11220151.5288
4.1.4. | Underpasses |  | 49249308.4302 | 38987035.6373
4.1.4.1 | Underpass 155 | 36 | 0 | 3848835.9366
4.1.4.2 | Underpass 040 | 36 | 0 | 3848835.9366
4.1.4.3 | Underpass 156 | 36 | 0 | 3848835.9366
4.1.4.4 | Tunel under station Jundiapeba | 36 | 0 | 4969631.4765
4.1.4.5 | CFTV - Underpasses line 11 | 36 | 0 | 63532.941
4.1.4.6 | Embankment and widening of underpass 137 | 48 | 0 | 22407363.4099
4.1.4.7 | Punctual improvements in the underpass 119 | 60 | 15322802.375 | 0
4.1.4.8 | Embankment and widening of underpass 118 | 60 | 15800593.8746 | 0
4.1.4.9 | Embankment and widening of underpass 154 | 60 | 2253296.9962 | 0
4.1.4.10 | Embankment and widening of underpass 88 | 60 | 15800593.8746 | 0
4.1.4.11 | CFTV - Underpasses line 12 | 60 | 72021.3098 | 0
4.2.. | Permanent Track |  | 699858562.8527 | 587678937.4142
4.2.1. | Recovery of the infrastructure and superstructure of the permanent track, Lines 11 and 12, extension of 89.570m double-track excluding the parking yards. It also includes 135 sets of AMV's, disregarding the Barra Funda-Luz and Luz-Brás segments. | 36 | 0 | 65912958.7314
4.2.2. | Segment Luz - km 0+000 / Brás km 2+240 (extension of 2.240 m double-track) | 60 | 35237525.3084 | 0
4.2.3. | Segment Engenheiro Gualberto - km 8+500 / Corinthians Itaquera - km 19+450 (extension 10.950 m double-track) | 60 | 58545395.8934 | 0
4.2.4. | Segment Tunel 3 km 23+040 / Guaianazes km 24+800 -(Extension of 1760m double-track) | 60 | 3406639.0245 | 0
4.2.5. | Segment Guaianazes km 24+800 / Suzano km 36+940 (Extension of 12.140m double-track. Rail TR 68 from km 25+000 to km 33+800 - Extension of 8.800m) | 84 | 156480224.2403 | 0
4.2.6. | Segment Suzano km 36+940 / Estudantes km 50+770 (Extension of 13.830m double-track) | 84 | 55770813.8205 | 98499559.6544
4.2.7. | Segment Brás - km 2+240/ SE Engenheiro Gualberto - km 8+500 (extension of 6.260 m with 4 tracks) | 84 | 114755548.9568 | 202675382.8002
4.2.8. | Construction of New Line Estudantes - Cezar of Souza - 4,26 km | 60 | 52866514.4931 | 0
4.2.9. | Segment SE Engenheiro Gualberto km 8+500 / USP Leste km 17+200 (Extension of 8.700 m double-track) | 60 | 72709595.9305 | 0
4.2.10. | Segment USP Leste km 17+200 / Engenheiro Manoel Feio km 33+150 (Extension of 15.950m double-track) | 84 | 37013391.4552 | 65371159.3916
4.2.11. | Segment USP Leste km 17+200 / Engenheiro Manoel Feio km 33+150 (Extension of 15.950m double-track) | 60 | 24062450.3276 | 35158045.3294
4.2.12. | Construction of New Line Calmon Viana - Suzano - 3,95 km | 72 | 20472465.965 | 32887150.597
4.2.13. | Construction of New Line Guarulhos Airport - Bonsucesso - 11 km | 96 | 68537997.4374 | 0
4.2.14. | Construction of New Line Engenheiro Goulart - Gabriela Mistral - 5,5 km | 48 | 0 | 87174680.9103
4.3.. | Auxiliary Vehicles and Equipment |  | 0 | 419713824.4987
4.3.1. | Auxiliary Vehicles and Equipment | 36 | 0 | 419713824.4987
5. | Venture 5: Rolling Stock |  | 48996197.4808 | 80802510.3119
5.1.. | Trains | 24 | 48996197.4808 | 80802510.3119
6. | Venture 6: Socio-environmental |  | 0 | 1761749294.9944
6.1.. | Expropriation between Bom Retiro | 48 | 0 | 525394486.518
6.2.. | Expropriation between Brás Cubas | 36 | 0 | 11579693.0856
6.3.. | Expropriation between Estudantes | 36 | 0 | 17650928.4452
6.4.. | Expropriation between Itaquaquecetuba | 36 | 0 | 1381779.3334
6.5.. | Expropriation between Jundiapeba | 36 | 0 | 5444401.7094
6.6.. | Expropriation between Lajeado | 48 | 0 | 70087815.5054
6.7.. | Expropriation between Mogi das Cruzes | 36 | 0 | 66162241.923
6.8.. | Expropriation between Suzano | 24 | 0 | 680577.9744
6.9.. | Expropriation between Cangaíba | 48 | 0 | 364756871.9807
6.10.. | Expropriation between between Guarulhos Airport - Jardim dos Eucaliptos | 24 | 0 | 32463646.4489
6.11.. | Expropriation between between Jardim dos Eucaliptos and São João | 60 | 0 | 260911281.1523
6.12.. | Expropriation between São João | 60 | 0 | 36652413.5782
6.13.. | Expropriation between between São João and Presidente Dutra | 60 | 0 | 185216676.4079
6.14.. | Expropriation between Presidente Dutra | 60 | 0 | 62752236.1089
6.15.. | Expropriation between between Presidente Dutra and Bonsucesso | 60 | 0 | 0
6.16.. | Expropriation between Bonsucesso | 60 | 0 | 7226364.2796
6.17.. | Expropriation between between Bonsucesso and segment final from lote | 60 | 0 | 3190262.1217
6.18.. | Expropriation between Jardim dos Eucaliptos | 60 | 0 | 60263819.593
6.19.. | Expropriation between between as estações Estudantes and César of Souza | 60 | 0 | 49933798.8286
7. | Venture 7: Projects |  | 69313111.0948 | 416001351.7348
7.1.. | Projects Line 11 | 24 | 47681076.4466 | 157267333.767
7.2.. | Projects Line 12 | 48 | 11106461.4486 | 132840920.5481
7.3.. | Projects Line 13 | 48 | 10525573.1996 | 125893097.4198
| Total |  | 3041047700.0872 | 9415904703.2896